## Define
Define: Identify the problem and the teams's scope.
Defects
A PO invoice needing correction after submission in Ariaba
A PO invoice not approved in Ariaba within discount threshold time
A Dev Manager spending more than 2 hours to validate and approve a PO invoice
Questions to consider: |  | A Dev Team spending more than 3 hours to validate and or correct a PO invoice
1) How are defects defined? How could you calculate SQL?
2) What is broken in this process?
3) What are some potential solutions to Hank's problems?
4) How might you calculate a business case / ROI? Is this problem worth fixing? Worth how much?

## Measure
Measure: Develop data collection plan and implement it.
Project:
Identify potential inputs, develop operational definitions, develop data measurement/collection plan, validate measurement system,
collect baseline data, calculate SQL (required for final project)
Project Requirements:
-Include Data Measurement Plan or Data Stratification Tree
-What type of data did you collect (cost, cycle time, changeover time, yield, machine utilization, inventory, etc.)?
-Was that data continuous or discrete?
-Did you collect your own data or did you use existing data?
-How much data did you collect and why? What is your ideal sample size using the sample size formula? Risks if you collected fewer samples?
-How was your data collected? Describe the methods you used to collect it.
-Where could you have measurement error? How much measurement error do you have? What did you do to minimize your measurement error?
Description: Validate your measurement system and collect baseline data.
Key Concepts:
Mapping the process/value-stream, forms of waste, measurement error, reproducibility, repeatability
Tools:
-Operational definitions
-Kappa
-Process map (detailed) -> Required
-Data measurement plan -> Required
-Data stratification tree -> Required
-1923547144
-Trendline chart
-Pareto chart
-Fishbone (cause/effect) diagram

## Measure-SQL
SQL for H1 of 2018
Defects
|  | Sigma Quality Level (SQL) |  |  |  | A PO invoice needing correction after submission in Ariaba
|  | Before: |  |  |  | A PO invoice not approved in Ariaba within discount threshold time
|  | After: |  |  |  | A Manager spending more than 2 hours to validate and approve a PO invoice
A Team spending more than 3 hours to validate and or correct a PO invoice
|  |  |  | H1-Q1 | H1-Q2 | H1-Total
SQL Before |  |  |  | 3 Sprints | 6 Sprints | 12 Sprints
Defect opportunities per unit: D = |  |  | 4 | 4 | 4 | 4 |  | SQL Definitions
Units produced per timeframe: U = |  |  | 36 | 9 | 18 | 36 | Unit: | A Unit is a PO; 4 possible Defect Units have been identified per PO Invoice Submission
Total possible defects per timeframe: D * U = |  |  | 144 |  |  |  | Timeframe: | Two week Sprint Cycle
Total actual defects in timeframe: A = |  |  | 91 | 28 | 52 | 91 | Units per timeframe: | 3 PO Invoices are created each Sprint Cycle based on the number of Sprint Teams managed by one Dev Manager
Defect-per-opportunity rate: A / DU = DPO = |  |  | 0.63194
Defects per million opportunities (DPMO): DPO x 1,000,000 = |  |  | 631944.4444
SQL value = |  |  | 1.1
SQL After |  |  |  | H2-Q1
Defect opportunities per unit: D =
Units produced per timeframe: U =
Total possible defects per timeframe: D * U =
Total actual defects in timeframe: A =
Defect-per-opportunity rate: A / DU = DPO =
Defects per million opportunities (DPMO): DPO x 1,000,000 =
SQL value =

## Measure-Data Measurement Plan
The GOAL is to REMOVE WASTE
Questions About Process |  |  | Stratification factors |  |  | This will improve EFFICIENCY and PRODUCTIVITY
|  |  | X Variables | Measurements
Does the PO invoice needing to be corrected indicate that the PO Invoice Approval Cycle time will exceed the discount threshold?
|  |  | PO Invoice Approval Cycle Time (days) | Count of Days between the ‘PO Submission Date’ and the ‘PO Approved Date’ minus 1 day |  | Cycle Time Definition
Does the number of different projects a Sprint team works on effect the approval cycle time? |  |  | PO Invoice Needed Correction (Y/N) | Indicator flag signifying if the PO invoice had to be sent back for correction
|  |  | Mgr PO Invoice Validation Time (hrs) | Hours recorded by the Manager |  | Start Cycle Time = PO Sprint End Date + 1 day. End Cycle Time = PO Approved/Received Date by Dev Manager Cycle Time = days between Start Cycle Time Date and End Cycle Time Date |  | PO Approval Cycle Time -> Referes to the vendor's PO invoice submission till the Dev Manager approves the invoice in Ariaba
|  | New PO Invoice | Team PO Invoice Validation Time (hrs) | Hours recorded by the Team
Does the number of User Stories per Sprint have an effect on the correctness of the PO Invoices? |  |  | PO Invoice User Story Count | Count of User Stories delivered for a given Sprint
|  | (Output Y) | PO Invoice Unique Project Count | Count of unique Projects that User Stories are aligned to as Project Deliverable Work
Does the number of Unique Projects per Sprint have an effect on the correctness of the PO Invoices?
Sources of Records
Does the number of User Stories per Sprint have an effect on the time Managers spend validating a PO invoice? |  |  |  | PO Invoice Approval Cycle Time (days) >>> Ariaba Procurement System
|  |  |  | PO Invoice Needed Correction (Y/N) >>> Ariaba Procurement System |  | Is cycle time impacted by the correctness of the PO?
Mgr PO Invoice Validation Time (hrs) >>> Clarity>Manager PO Invoice Approval & Validation Tasks
Does the number of Unique Stories per Sprint have effect on the time Managers spend validating a PO invoice?
Team PO Invoice Validation Time (hrs) >>> Clarity>Team PO Invoice Validation Tasks
Does the submitter have all necessary data requirements for DevManager approvals?
PO Invoice User Story Count >>> Rally>Delivery Team Sprint Project Repositories>Sprints Dashboard
PO Invoice Unique Project Count >>> Rally>Delivery Team Sprint Project Repositories>User Story>Project ID field
Does the number of different projects a Sprint team works on effect the approval cycle time?
Thoughts on questions? |  |  |  | Sigma Quality Level (SQL) | Defect Definition
Number of Sprint Teams? |  |  |  | Before: | PO process is not complete in 15 days PO information is not correct |  | ACTION REQUIRED: Please validate that the PO information is correct. If this Purchase Order needs to be corrected, please edit or cancel your PO in Procurement OnDemand.
Agile Sprint Cycle Time (2 weeks vs 3 or 4) |  |  |  | After:
Agile Sprint Team Size?
Number of User Stories per Sprint?
Number of different projects per Sprint? | [6 empty] | For questions regarding Training, FAQs, How to Videos, Business Processes and Procurement Policies, visit the Procurement OnDemand Resource Page.
Is the data complete in Rally? |  |  |  | SQL Before
Are project and SAP codes correctly assigned? |  |  |  | Defect opportunities per unit: D =
Is cycle time effected by manually sending email notifications? |  |  |  | Units produced per timeframe: U =
Is the current PO broken down by Sprint team? |  |  |  | Total possible defects per timeframe: D * U =
Is the current PO identifiable to a sprint and team for it's user stories? |  |  |  | Total actual defects in timeframe: A = |  |  | Payment Terms 2% disc in 15 days rct date else 60 days
Is the time to submit a PO a factor on cycle time? |  |  |  | Defect-per-opportunity rate: A / DU = DPO =
Defects per million opportunities (DPMO): DPO x 1,000,000 =
SQL value =
Operational Definitions
What is the measurement process?
How to do it? When to do it? Who does it? |  |  |  | SQL After
Defect opportunities per unit: D =
Units produced per timeframe: U =
Total possible defects per timeframe: D * U =
Total actual defects in timeframe: A =
Defect-per-opportunity rate: A / DU = DPO =
Defects per million opportunities (DPMO): DPO x 1,000,000 =
SQL value =
8 Types of WASTE
Wastes: DOWNTIME | Services Industry
Defects | errors, missinformation
Overproduction | information overload
Waiting | delays, meeting overrun
Non-utilized Skills | wrong resource allocation
Transportation | travel/ search activities
Inventory | excessive multitasking
Motion | unnecessary action
Excess Processing | duplication/ excess work

## Measure-Data Collection
Data Collection | [19 empty] | *Within 15 biz day goal | *3 Resources total time | *1 Resources total time |  | Disc Threshold Days
PRE-Process Improvement | [23 empty] | 19
Sample | PO ID | Sprint | Sprint Start Date | Sprint End Date | Sprint Team | PO Est. Cost ($) | PO Est. LOE (hrs) | PO Act. Cost ($) | PO Act. LOE (hrs) | Disc Opportunity (2%) | Disc Achieved ($) | User Stories Count | Unique Project Count | PO Line Item Count | PO Submission Date | PO Approved Date | Needed Correction (Y/N) | PO Approval Cycle Time (days) | PO Cycle Time (days) | Within Disc Threshold (Y/N) | Team Validation Meetings Time (hrs) | Mgr Validation Time (hrs)
1 | PO1 | EIT 1 | 2018-01-03 | 2018-01-23 | Gamma Squad | 43382.92 | 292 | 44422 | 299 | 8884.4 | 0 | 10 | 2 | 2 | 2018-01-29 | 2018-02-28 | Y | 29 | 35 | N | 3 | 3 |  |  | Data Type | Data Attribute | Column Definitions
2 | PO2 | EIT 1 | 2018-01-03 | 2018-01-23 | Omega Squad | 25619.7 | 299 | 26280 | 299 | 5256 | 0 | 15 | 2 | 2 | 2018-01-30 | 2018-03-02 | Y | 30 | 37 | N | 4 | 4 |  |  | Discrete | Sprint | Sprint squence name for the EIT department
3 | PO3 | EIT 1 | 2018-01-03 | 2018-01-23 | Theta Squad | 41418.26 | 393 | 42735 | 405.5 | 8547 | 0 | 8 | 2 | 2 | 2018-01-30 | 2018-03-02 | Y | 30 | 37 | N | 3 | 2 |  |  | Continuous | Sprint Start Date | Sprints are in two week cycles starting wednesdays
4 | PO4 | EIT 2 | 2018-01-24 | 2018-02-06 | Gamma Squad | 53522.36 | 384.5 | 50307 | 359 | 10061.4 | 0 | 14 | 3 | 3 | 2018-02-12 | 2018-03-09 | Y | 24 | 30 | N | 4 | 3 |  |  | Continuous | Sprint End Date | Sprint cycle end date, every other Tuesday
5 | PO5 | EIT 2 | 2018-01-24 | 2018-02-06 | Omega Squad | 28196.47 | 319 | 26825 | 303.5 | 5365 | 0 | 15 | 2 | 2 | 2018-02-13 | 2018-03-09 | Y | 23 | 30 | N | 4 | 3 |  |  | Discrete | Sprint Team | Name of the Sprint Team the PO is billed for
6 | PO6 | EIT 2 | 2018-01-24 | 2018-02-06 | Theta Squad | 45320 | 400 | 45887 | 405 | 9177.4 | 0 | 6 | 4 | 4 | 2018-02-09 | 2018-03-06 | Y | 24 | 27 | N | 3 | 2 |  |  | Discrete | User Stories Count | Number of Rally User Stories complete for given sprint
7 | PO7 | EIT 3 | 2018-02-07 | 2018-02-20 | Gamma Squad | 55285.4 | 426 | 45452 | 346 | 9090.4 | 0 | 15 | 3 | 3 | 2018-02-27 | 2018-03-23 | Y | 23 | 30 | N | 4 | 4 |  |  | Discrete | Unique Project Count | Number of Unique Projects the User Stories align to
8 | PO8 | EIT 3 | 2018-02-07 | 2018-02-20 | Omega Squad | 26377.45 | 321.5 | 26825 | 327 | 5365 | 0 | 15 | 2 | 2 | 2018-02-27 | 2018-03-23 | N | 23 | 30 | N | 1 | 3 |  |  | Discrete | PO Line Item Count | Number of line items displayed on Arabia PO invoice
9 | PO9 | EIT 3 | 2018-02-07 | 2018-02-20 | Theta Squad | 47485.9 | 490 | 45887 | 473.5 | 9177.4 | 0 | 10 | 4 | 4 | 2018-02-23 | 2018-03-16 | Y | 20 | 23 | N | 1 | 3 |  |  | Continuous | PO Submission Date | Date the PO was submitted by the Vendor
10 | PO10 | EIT 4 | 2018-02-21 | 2018-03-06 | Gamma Squad | 48706.27 | 360.5 | 42636 | 316 | 8527.2 | 0 | 11 | 3 | 3 | 2018-03-12 | 2018-04-02 | Y | 20 | 26 | N | 3 | 3 |  |  | Continuous | PO Approved Date | Date the PO was approved by Dev Manager of Sprint Team
11 | PO11 | EIT 4 | 2018-02-21 | 2018-03-06 | Omega Squad | 36480.34 | 397 | 30185 | 328.5 | 6037 | 0 | 11 | 2 | 2 | 2018-03-12 | 2018-04-02 | Y | 20 | 26 | N | 3 | 3 |  |  | Discrete | Needed Correction | Flag specifing if the PO had errors and needed correction
12 | PO12 | EIT 4 | 2018-02-21 | 2018-03-06 | Theta Squad | 47884.93 | 428.5 | 42185 | 377.5 | 8437 | 0 | 13 | 1 | 1 | 2018-03-09 | 2018-03-30 | N | 20 | 23 | N | 1.5 | 3 |  |  | Continuous | PO Approval Cycle Time | Days between PO submission date and the Dev Manager approving the PO
13 | PO13 | EIT 5 | 2018-03-07 | 2018-03-20 | Gamma Squad | 46003.73 | 316.5 | 48017 | 331 | 9603.4 | 0 | 8 | 2 | 2 | 2018-03-23 | 2018-04-17 | Y | 24 | 27 | N | 3 | 3 |  |  | Continuous | PO Cycle Time | Total cycle time to complete the PO billing process. Starts 1 day post sprint end date
14 | PO14 | EIT 5 | 2018-03-07 | 2018-03-20 | Omega Squad | 34222.51 | 390 | 29835 | 340 | 5967 | 0 | 13 | 2 | 2 | 2018-03-27 | 2018-04-17 | Y | 20 | 27 | N | 4 | 4 |  |  | Discrete | Within Disc Threshold | Flag indicator specifing if the PO cycle time was within the discount threshold of 15 biz days
15 | PO15 | EIT 5 | 2018-03-07 | 2018-03-20 | Theta Squad | 42389.05 | 407 | 38745 | 372 | 7749 | 0 | 8 | 1 | 1 | 2018-03-23 | 2018-04-17 | Y | 24 | 27 | N | 1 | 2 |  |  | Continuous | Team Validation Meetings | Cumilative team time to conduct meetings to validate PO line item data
16 | PO16 | EIT 6 | 2018-03-21 | 2018-04-03 | Gamma Squad | 52955.45 | 306 | 45631 | 281 | 9126.2 | 0 | 9 | 4 | 4 | 2018-04-06 | 2018-04-27 | Y | 20 | 23 | N | 3 | 4 |  |  | Continuous | Mgr Validation Time | Manager time to pull User Story data from Rally and validate it against PO line items
17 | PO17 | EIT 6 | 2018-03-21 | 2018-04-03 | Omega Squad | 34311.69 | 481.5 | 29360 | 412 | 5872 | 0 | 11 | 2 | 2 | 2018-04-09 | 2018-05-04 | Y | 24 | 30 | N | 4 | 4 |  |  | Continuous | PO Est. Cost ($) | Vendor estimated calculated cost based on Sprint Team Resources needed to deliver User Stories for Sprint
18 | PO18 | EIT 6 | 2018-03-21 | 2018-04-03 | Theta Squad | 40789.88 | 262.5 | 37915 | 244 | 7583 | 7583 | 6 | 1 | 1 | 2018-04-06 | 2018-04-17 | N | 10 | 13 | Y | 1 | 1 |  |  | Continuous | PO Act. Cost ($) | Vendor actual calculated cost based on Sprint Team Resources needed to deliver User Stories for Sprint
19 | PO19 | EIT 7 | 2018-04-04 | 2018-04-17 | Gamma Squad | 48697.2 | 294 | 46973 | 255.7 | 9394.6 | 0 | 10 | 5 | 5 | 2018-04-23 | 2018-05-15 | Y | 21 | 27 | N | 4 | 4 |  |  | Continuous | PO Est. LOE (hrs) | Vendor calculated sum of estimated level of efforts to deliver each User Story for a Sprint
20 | PO20 | EIT 7 | 2018-04-04 | 2018-04-17 | Omega Squad | 21643.51 | 282 | 24905 | 324.5 | 4981 | 0 | 11 | 2 | 2 | 2018-04-23 | 2018-05-15 | Y | 21 | 27 | N | 4 | 4 |  |  | Continuous | PO Act. LOE (hrs) | Vendor calculated sum of actual level of efforts to deliver each User Story for a Sprint
21 | PO21 | EIT 7 | 2018-04-04 | 2018-04-17 | Theta Squad | 36031.44 | 297 | 34272 | 282.5 | 6854.4 | 6854.4 | 5 | 1 | 1 | 2018-04-20 | 2018-05-08 | N | 17 | 20 | Y | 1 | 1
22 | PO22 | EIT 8 | 2018-04-18 | 2018-05-01 | Gamma Squad | 49495.95 | 303.5 | 49220 | 302 | 9844 | 0 | 10 | 3 | 3 | 2018-05-07 | 2018-05-29 | Y | 21 | 27 | N | 4 | 4
23 | PO23 | EIT 8 | 2018-04-18 | 2018-05-01 | Omega Squad | 20604.61 | 251 | 20933 | 255 | 4186.6 | 0 | 11 | 1 | 1 | 2018-05-07 | 2018-05-29 | N | 21 | 27 | N | 1 | 3
24 | PO24 | EIT 8 | 2018-04-18 | 2018-05-01 | Theta Squad | 37517.21 | 379 | 35685 | 360.5 | 7137 | 0 | 7 | 2 | 2 | 2018-05-04 | 2018-05-29 | Y | 24 | 27 | N | 1 | 2
25 | PO25 | EIT 9 | 2018-05-02 | 2018-05-15 | Gamma Squad | 56974.53 | 387 | 48260 | 329.5 | 9652 | 0 | 14 | 4 | 4 | 2018-05-21 | 2018-06-12 | Y | 21 | 27 | N | 4 | 5
26 | PO26 | EIT 9 | 2018-05-02 | 2018-05-15 | Omega Squad | 24798.53 | 285.5 | 19150 | 220.5 | 3830 | 0 | 10 | 1 | 1 | 2018-05-18 | 2018-06-12 | N | 24 | 27 | N | 1 | 3
27 | PO27 | EIT 9 | 2018-05-02 | 2018-05-15 | Theta Squad | 28811.25 | 177 | 30439 | 187 | 6087.8 | 6087.8 | 5 | 2 | 2 | 2018-05-18 | 2018-06-01 | N | 13 | 16 | Y | 1 | 1
28 | PO28 | EIT 10 | 2018-05-16 | 2018-05-29 | Gamma Squad | 54053.36 | 445 | 48260 | 402 | 9652 | 0 | 15 | 4 | 4 | 2018-06-04 | 2018-06-29 | Y | 24 | 30 | N | 4 | 5
29 | PO29 | EIT 10 | 2018-05-16 | 2018-05-29 | Omega Squad | 27749.46 | 313 | 23095 | 260.5 | 4619 | 4619 | 4 | 1 | 1 | 2018-06-01 | 2018-06-12 | N | 10 | 13 | Y | 1 | 2
30 | PO30 | EIT 10 | 2018-05-16 | 2018-05-29 | Theta Squad | 51507.18 | 305 | 32002 | 189.5 | 6400.4 | 6400.4 | 5 | 2 | 2 | 2018-06-01 | 2018-06-12 | N | 10 | 13 | Y | 1 | 1
31 | PO31 | EIT 11 | 2018-05-30 | 2018-06-12 | Gamma Squad | 44117.79 | 325.5 | 43956 | 324 | 8791.2 | 0 | 15 | 4 | 4 | 2018-06-18 | 2018-07-13 | Y | 24 | 30 | N | 4 | 5
32 | PO32 | EIT 11 | 2018-05-30 | 2018-06-12 | Omega Squad | 33364.34 | 317.5 | 21960 | 207 | 4392 | 4392 | 6 | 1 | 1 | 2018-06-15 | 2018-07-03 | N | 17 | 20 | Y | 1 | 2
33 | PO33 | EIT 11 | 2018-05-30 | 2018-06-12 | Theta Squad | 37863.46 | 264 | 34995 | 244 | 6999 | 0 | 6 | 2 | 2 | 2018-06-15 | 2018-07-13 | Y | 27 | 30 | N | 2 | 1
34 | PO34 | EIT 12 | 2018-06-13 | 2018-06-26 | Gamma Squad | 49582.74 | 344.5 | 42597 | 296.5 | 8519.4 | 0 | 9 | 3 | 3 | 2018-07-02 | 2018-07-27 | Y | 24 | 30 | N | 4 | 3
35 | PO35 | EIT 12 | 2018-06-13 | 2018-06-26 | Omega Squad | 27483 | 195.5 | 23350 | 166.1 | 4670 | 0 | 7 | 1 | 1 | 2018-06-29 | 2018-07-27 | Y | 27 | 30 | N | 2 | 3
36 | PO36 | EIT 12 | 2018-06-13 | 2018-06-26 | Theta Squad | 37269.17 | 365.5 | 37779 | 370.5 | 7555.8 | 7555.8 | 8 | 1 | 1 | 2018-06-29 | 2018-07-07 | N | 7 | 10 | Y | 1 | 2 | End of H1 2018
37 | PO37 | EIT 13 | 2018-06-27 | 2018-07-10 | Gamma Squad | 49598.13 | 235 | 40618.33 | 189.5 | 8123.666 | 0 | 7 | 4 | 4 | 2018-07-16 | 2018-08-07 | Y | 21 | 27 | N | 3 | 3
38 | PO38 | EIT 13 | 2018-06-27 | 2018-07-10 | Omega Squad | 13267.61 | 328 | 12560 | 310.5 | 2512 | 0 | 11 | 1 | 1 | 2018-07-13 | 2018-08-07 | Y | 24 | 27 | N | 3 | 3
39 | PO39 | EIT 13 | 2018-06-27 | 2018-07-10 | Theta Squad | 0 | 416 | 0 | 305 | 0 | 0 | 9 | 1 | 1 | 2018-07-13 | 2018-07-27 | N | 13 | 16 | Y | 1 | 2
Totals: | [5 empty] | 1500782.78 | 13185 | 1370138.33 | 12001.8 | 274027.666 | 43492.4 | [5 empty] | 27 |  |  | 8 | 98.5 | 113 | sum or count
[6 empty] | 38481.6097 | 338.0769 | 35131.7521 | 307.7385 | 7026.3504 | 1115.1897 | 9.8205 | 2.2564 | 2.2564 |  |  | 69.23% | 21 | 25.6923 | 20.51% | 2.5256 | 2.8974 | avg
[6 empty] | 12707.1363 | 71.9933 | 11547.4916 | 70.2314 |  | 2469.4117 | 3.3472 | 1.1634 | 1.1634 |  |  |  | 5.4628 | 6.3955 |  | 1.3026 | 1.1191 | std dev |  |  |  |  | Total Cycles: |  | 36
[6 empty] | 56974.53 | 313 | 50307 | 307.4 |  | 7583 | 11 | 4 | 4 |  |  |  | 23 | 27 |  | 3 | 4 | range |  |  | Defects, H1 2018 (12 Sprints, 36 POs) |  |  |  | Counts | Defects, H1-Q1 2018 (6 Sprints, 18 POs) |  | Counts | Defects, H1-Q2 2018 (6 Sprints, 18 POs) |  | Counts
[10 empty] | 5911.1607 |  |  |  |  | Accuracy Rate: |  | 30% | [8 empty] | A PO invoice needing correction after submission in Ariaba |  |  |  | 25 | A PO invoice needing correction after submission in Ariaba |  | 15 | A PO invoice needing correction after submission in Ariaba |  | 10
[26 empty] | A PO invoice not approved in Ariaba within discount threshold time |  |  |  | 29 | A PO invoice not approved in Ariaba within discount threshold time |  | 17 | A PO invoice not approved in Ariaba within discount threshold time |  | 12
[26 empty] | A Dev Manager spending more than 2 hours to validate and approve a PO invoice |  |  |  | 24 | A Dev Manager spending more than 2 hours to validate and approve a PO invoice |  | 14 | A Dev Manager spending more than 2 hours to validate and approve a PO invoice |  | 10
[20 empty] | *Within 15 biz day goal | *3 Resources total time | *1 Resources total time |  |  |  | A Dev Team spending more than 3 hours to validate and or correct a PO invoice |  |  |  | 13 | A Dev Team spending more than 3 hours to validate and or correct a PO invoice |  | 6 | A Dev Team spending more than 3 hours to validate and or correct a PO invoice |  | 7
POST-Process Improvement | [28 empty] | Total: | 91 |  | Total: | 52 |  | Total: | 39
Sample | PO ID | Sprint | Sprint Start Date | Sprint End Date | Sprint Team Count | PO Est. Cost ($) | PO Est. LOE (hrs) | PO Act. Cost ($) | PO Act. LOE (hrs) | Disc Opportunity (2%) | Disc Achieved ($) | User Stories Count | Unique Project Count | PO Line Item Count | PO Submition Date | PO Approved Date | Needed Correction (Y/N) | PO Approval Cycle Time (days) | PO Cycle Time (days) | Within Disc Threshold (Y/N) | Team Validation Meetings Time (hrs) | Mgr Validation Time (hrs)
1 | PO40 | EIT 14 | 2018-07-11 | 2018-07-24 | Gamma Squad | 41685.39 | 163.5 | 39038 | 152.5 | 7807.6 | 7807.6 | 11 | 2 | 2 | 2018-07-27 | 2018-08-10 | N | 13 | 16 | Y | 2 | 1 | [8 empty] | Defects, H1-Q1:H1 2018 (3 Sprints, 9 POs) |  | Counts
2 | PO41 | EIT 14 | 2018-07-11 | 2018-07-24 | Omega Squad | 16596.13 | 294 | 12560 | 222.5 | 2512 | 2512 | 10 | 1 | 1 | 2018-07-27 | 2018-08-10 | N | 13 | 16 | Y | 0 | 1 | [8 empty] | A PO invoice needing correction after submission in Ariaba |  | 8
3 | PO42 | EIT 14 | 2018-07-11 | 2018-07-24 | Theta Squad | 41195.35 | 347 | 35022 | 295 | 7004.4 | 7004.4 | 8 | 1 | 1 | 2018-07-27 | 2018-08-10 | N | 13 | 16 | Y | 0 | 0.5 | [8 empty] | A PO invoice not approved in Ariaba within discount threshold time |  | 9
4 | PO43 | EIT 15 | 2018-07-25 | 2018-08-07 | Gamma Squad | 66633.47 | 196 | 51913 | 152 | 10382.6 | 10382.6 | 8 | 2 | 2 | 2018-08-10 | 2018-08-21 | N | 10 | 13 | Y | 2 | 1 |  |  | 57 | [5 empty] | A Dev Manager spending more than 2 hours to validate and approve a PO invoice |  | 7
5 | PO44 | EIT 15 | 2018-07-25 | 2018-08-07 | Omega Squad | 15387.38 | 361 | 15430 | 362 | 3086 | 3086 | 6 | 1 | 1 | 2018-08-10 | 2018-08-21 | N | 10 | 13 | Y | 0 | 0.5 | [8 empty] | A Dev Team spending more than 3 hours to validate and or correct a PO invoice |  | 4
6 | PO45 | EIT 15 | 2018-07-25 | 2018-08-07 | Theta Squad | 35834.23 | 310 | 30680 | 268 | 6136 | 6136 | 8 | 2 | 2 | 2018-08-10 | 2018-08-24 | Y | 13 | 16 | Y | 2 | 1.5 | [9 empty] | Total: | 28
7 | PO46 | EIT 16 | 2018-08-08 | 2018-08-21 | Gamma Squad | 27689 | 155.5 | 27423 | 151 | 5484.6 | 5484.6 | 7 | 3 | 3 | 2018-08-24 | 2018-09-04 | N | 10 | 13 | Y | 1 | 1
8 | PO47 | EIT 16 | 2018-08-08 | 2018-08-21 | Omega Squad | 27749.46 | 340.5 | 36287 | 411 | 7257.4 | 7257.4 | 8 | 1 | 1 | 2018-08-24 | 2018-09-04 | N | 10 | 13 | Y | 0 | 0.5 | [8 empty] | Defects, H1-Q1:H2 2018 (3 Sprints, 9 POs) |  | Counts
9 | PO48 | EIT 16 | 2018-08-08 | 2018-08-21 | Theta Squad | 32598 | 201 | 26823 | 159 | 5364.6 | 5364.6 | 4 | 1 | 1 | 2018-08-24 | 2018-09-04 | N | 10 | 13 | Y | 0 | 0.25 | [8 empty] | A PO invoice needing correction after submission in Ariaba |  | 7
10 | PO49 | EIT 17 | 2018-08-22 | 2018-09-04 | Gamma Squad | 49598.13 | 169 | 49220 | 182 | 9844 | 9844 | 9 | 2 | 2 | 2018-09-07 | 2018-09-14 | N | 6 | 9 | Y | 2 | 1 | [8 empty] | A PO invoice not approved in Ariaba within discount threshold time |  | 8
11 | PO50 | EIT 17 | 2018-08-22 | 2018-09-04 | Omega Squad | 13267.61 | 340.5 | 20933 | 411 | 4186.6 | 4186.6 | 10 | 1 | 1 | 2018-09-07 | 2018-09-18 | Y | 10 | 13 | Y | 3 | 2 | [8 empty] | A Dev Manager spending more than 2 hours to validate and approve a PO invoice |  | 7
12 | PO51 | EIT17 | 2018-08-22 | 2018-09-04 | Theta Squad | 32598 | 201 | 35685 | 159 | 7137 | 7137 | 4 | 1 | 1 | 2018-09-07 | 2018-09-14 | N | 6 | 9 | Y | 0 | 0.25 | [8 empty] | A Dev Team spending more than 3 hours to validate and or correct a PO invoice |  | 2
13 | PO52 | EIT 18 | 2018-09-05 | 2018-09-18 | Gamma Squad | 46003.73 | 250 | 48017 | 257 | 9603.4 | 9603.4 | 10 | 3 | 3 | 2018-09-21 | 2018-09-25 | N | 3 | 6 | Y | 1 | 1 | [9 empty] | Total: | 24
14 | PO53 | EIT 18 | 2018-09-05 | 2018-09-18 | Omega Squad | 34222.51 | 617 | 29835 | 352 | 5967 | 5967 | 15 | 1 | 1 | 2018-09-21 | 2018-09-25 | N | 3 | 6 | Y | 1 | 1
15 | PO54 | EIT 18 | 2018-09-05 | 2018-09-18 | Theta Squad | 42389.05 | 476 | 38745 | 178 | 7749 | 7749 | 4 | 1 | 1 | 2018-09-21 | 2018-09-25 | N | 3 | 6 | Y | 0 | 0.25
Totals: | [5 empty] | 523447.44 | 4422 | 497611 | 3712 | 99522.2 | 89202.6 | 122 |  |  |  |  | 2 |  |  | 15 |  | 0.85 | total or count
avg | [5 empty] | 34896.496 | 294.8 | 33174.0667 | 247.4667 | 6634.8133 | 9133.539 | 8.1333 | 1.5333 | 1.5333 |  |  | 13.33% | 8.8667 | 11.8667 | 100% | 0.93333 | 0.83929 | avg |  | Defects, H2:Q2 2018 (5 Sprints, 15 POs) |  |  |  | Counts
std dev | [5 empty] | 14108.9962 | 128.1733 | 11631.7889 | 97.5153 | 2326.3578 | 2326.3578 | 2.9729 | 0.74322 | 0.74322 |  |  |  | 3.7391 | 3.7391 |  | 1.0328 | 0.48917 | std dev |  | A PO invoice needing correction after submission in Ariaba |  |  |  | 2
range | [5 empty] | 53365.86 | 461.5 | 39353 | 260 | 7870.6 | 7870.6 | 11 | 2 | 2 |  |  |  | 10 | 10 |  | 3 | 1.75 | range |  | A PO invoice not approved in Ariaba within discount threshold time |  |  |  | 0
[15 empty] | Accuracy Rate: |  | 86.67% | [7 empty] | A Dev Manager spending more than 1 hours to validate and approve a PO invoice |  |  |  | 2
[25 empty] | A Dev Team spending more than 3 hours to validate and or correct a PO invoice |  |  |  | 0
[28 empty] | Total: | 4
[25 empty] | SQL After |  |  |  |  | H2-Q1
[25 empty] | Defect opportunities per unit: D = |  |  |  | 4
[25 empty] | Units produced per timeframe: U = |  |  |  | 5
[25 empty] | Total possible defects per timeframe: D * U = |  |  |  | 20
[25 empty] | Total actual defects in timeframe: A = |  |  |  | 4
[25 empty] | Defect-per-opportunity rate: A / DU = DPO = |  |  |  | 0.2
[25 empty] | Defects per million opportunities (DPMO): DPO x 1,000,000 = |  |  |  | 200000
[25 empty] | SQL value = |  |  |  | 2.3
Formulas:
PO Approval Cycle Time (days) = (DATEDIF([PO Submission Date],[PO Approved Date],"d")-1)
PO Approval Cycle Time (days) = DATEDIF([PO Submission Date],[PO Approved Date],"d")-1
PO Cycle Time (days) = (DATEDIF([Sprint End Date],[PO Approved Date],"d")-1)
PO Cycle Time (days) = DATEDIF([Sprint End Date],[PO Approved Date],"d")-1

## Measure-SoftTools
Defects
A PO invoice needing correction after submission in Ariaba
A PO invoice not approved in Ariaba within discount threshold time
A Dev Manager spending more than 2 hours to validate and approve a PO invoice
A Dev Team spending more than 3 hours to validate and or correct a PO invoice
PO ID | PO Approval Cycle Time (days) | Discount Threshold (days)
PO1 | 29 | 19 | [10 empty] | PO Approval Cycle Time (days)
PO2 | 30 | 19
PO3 | 30 | 19 | [10 empty] | Mean | 21.1389
PO4 | 24 | 19 | [10 empty] | Standard Error | 0.91734
PO5 | 23 | 19 | [10 empty] | Median | 22
PO6 | 24 | 19 | [10 empty] | Mode | 24
PO7 | 23 | 19 | [10 empty] | Standard Deviation | 5.504
PO8 | 23 | 19 | [10 empty] | Sample Variance | 30.2944
PO9 | 20 | 19
PO10 | 20 | 19
PO11 | 20 | 19 | [10 empty] | Range | 23
PO12 | 20 | 19 | [10 empty] | Minimum | 7
PO13 | 24 | 19 | [10 empty] | Maximum | 30
PO14 | 20 | 19
PO15 | 24 | 19 | [10 empty] | Count | 36
PO16 | 20 | 19
PO17 | 24 | 19
PO18 | 10 | 19
PO19 | 21 | 19
PO20 | 21 | 19
PO21 | 17 | 19
PO22 | 21 | 19
PO23 | 21 | 19
PO24 | 24 | 19
PO25 | 21 | 19
PO26 | 24 | 19
PO27 | 13 | 19
PO28 | 24 | 19
PO29 | 10 | 19
PO30 | 10 | 19
PO31 | 24 | 19
PO32 | 17 | 19
PO33 | 27 | 19
PO34 | 24 | 19
PO35 | 27 | 19
PO36 | 7 | 19
Histogram?
PO ID
| User Stories Count | Unique Project Count
PO1 | 10 | 2
PO2 | 15 | 2
PO3 | 8 | 2
PO4 | 14 | 3
PO5 | 15 | 2
PO6 | 6 | 4
PO7 | 15 | 3
PO8 | 15 | 2
PO9 | 10 | 4
PO10 | 11 | 3
PO11 | 11 | 2
PO12 | 13 | 1
PO13 | 8 | 2
PO14 | 13 | 2
PO15 | 8 | 1
PO16 | 9 | 4
PO17 | 11 | 2
PO18 | 6 | 1
PO19 | 10 | 5
PO20 | 11 | 2
PO21 | 5 | 1
PO22 | 10 | 3
PO23 | 11 | 1
PO24 | 7 | 2
PO25 | 14 | 4
PO26 | 10 | 1
PO27 | 5 | 2
PO28 | 15 | 4
PO29 | 4 | 1
PO30 | 5 | 2
PO31 | 15 | 4
PO32 | 6 | 1
PO33 | 6 | 2
PO34 | 9 | 3
PO35 | 7 | 1
PO36 | 8 | 1
PO ID
| Needed Correction (Y/N) | Within Disc Threshold (Y/N) |  |  | PO ID | Needed Correction (Y/N) | Within Disc Threshold (Y/N)
PO1 | Y | N |  |  | PO40 | N | N
PO2 | Y | N |  |  | PO41 | N | N
PO3 | Y | N |  |  | PO42 | N | N
PO4 | Y | N |  |  | PO43 | N | N
PO5 | Y | N |  |  | PO44 | N | N
PO6 | Y | N |  |  | PO45 | Y | N
PO7 | Y | N |  |  | PO46 | N | N
PO8 | N | N |  |  | PO47 | N | N
PO9 | Y | N |  |  | PO48 | N | N
PO10 | Y | N |  |  | PO49 | N | N
PO11 | Y | N |  |  | PO50 | Y | N
PO12 | N | N |  |  | PO51 | N | N
PO13 | Y | N |  |  | PO52 | N | N
PO14 | Y | N |  |  | PO53 | N | N
PO15 | Y | N |  |  | PO54 | N | N
PO16 | Y | N |  |  |  | 2 | 0
PO17 | Y | N |  |  |  | 13.33% | 0% |  | % Needed Correction | % Did Not Need Correction
PO18 | N | Y | [6 empty] | 13.33% | 86.67%
PO19 | Y | N
PO20 | Y | N
PO21 | N | Y
PO22 | Y | N
PO23 | N | N
PO24 | Y | N
PO25 | Y | N
PO26 | N | N
PO27 | N | Y
PO28 | Y | N
PO29 | N | Y
PO30 | N | Y
PO31 | Y | N
PO32 | N | Y
PO33 | Y | N
PO34 | Y | N
PO35 | Y | N
PO36 | N | Y
| 25 | 7
| 69.44% | 19.44%
| Type | Percent Yes | Percent No
| Correction | 69 | 31
| Within Threshold | 19 | 81
|  | Needed Correction | Within Threshold
| Percent Yes | 69% | 19%
| Percent No | 31% | 81%
After Process Improvements
| PO Approval Cycle Time (days) | Discount Threshold (days)
PO ID | [10 empty] | PO Invoice Approval Cycle Time
PO40 | 13 | 19
PO41 | 13 | 19 | [8 empty] | Mean | 8.8667
PO42 | 13 | 19 | [8 empty] | Standard Error | 0.96543
PO43 | 10 | 19 | [8 empty] | Standard Deviation | 3.7391
PO44 | 10 | 19 | [8 empty] | Sample Variance | 13.981
PO45 | 13 | 19 | [8 empty] | Range | 10
PO46 | 10 | 19 | [8 empty] | Minimum | 3
PO47 | 10 | 19 | [8 empty] | Maximum | 13
PO48 | 10 | 19 | [8 empty] | Count | 15
PO49 | 6 | 19
PO50 | 10 | 19
PO51 | 6 | 19
PO52 | 3 | 19
PO53 | 3 | 19
PO54 | 3 | 19

## Analyze
Tools
| Analyze: Determine root cause; identify and verify critical variables | Hypothesis Statements
|  | Dev Manager Validation Cycle Time: -Is my average dev manager validation process time (avg = , std dev = , ) performing well versus our goal (avg less than 2 hrs)? Ho = Ha = | Chi-Square Test: Test for Independence
if two variables are related or statistically independent. Ho: Cat v1 and Cat v2 are independent (no relationship) Ha: Categorical v1 and Categorical v2 are not independent (i.e. there is a relationship)
Project:
1: Write a null and alternative hypothesis statement
2: Utilize the sample size formula. |  | Dev Team PO Validation Cycle Time: -Is my average dev team PO validation process cycle time (avg = , std dev = ) performing well versus our goal (avg less than 3 hrs)? Ho = Ha =
3: Use regression to identify relationships between the output (y) and inputs (x’s)
Project Requirements:
-What tools did you use to analyze the data? Why? |  | PO Invoices needing correction: Is my average PO Invoice that need correction (avg = , std dev = ) performing well versus goal (average less than 20%)? Ho = Ha =
-What is the data telling you? What did you discover?
-What is the SQL for the old and new process? |  |  | Confidence Intervals
Description: |  | PO Invoices not approved within discount threshold: Is my average PO Approval process cycle time (avg = , std dev = ) performing well versus goal (avg less than 15 days)? Ho = Ha =
Analyze, describe, and present the data to discover the root causes(s), identify/prioritize critical inputs (x’s), determine the inputs impact on the output.
Key Concepts:
1: Inferential statistics, common distributions, developing a hypothesis, determining the likelihood some event happens based on a sample (calculating probabilities), Using the normal distribution as the ‘go to’ distribution. |  | Hypothesis Statements
|  | PO Invoice Needing Correction vs. PO Invoice Approval Within Threshold: -Is PO invoice needed correction associated with PO invoices not being approved within our threshold time? Ho = Ha = | Correlation
2: Collecting sample data, how confidence intervals and sample size are related
3: Determining input’s (x) impact on the output (y).
Tools: |  | Number of User Stories vs. PO Invoice Approval Within Threshold: -Is the number of User Stories for a given Sprint PO associated with PO invoices not being approved withn our threshold time? Ho = Ha =
1: Hypothesis testing, Chi-square test for independence
2: Confidence intervals
3: Correlation, Simple linear regression, Multiple regression, Scatterplot, Trend/line chart, Pareto chart, Fishbone (cause/effect) diagram |  |  | Simple Linear Regression
Number of User Stories vs. PO Invoice Needing Correction: -Is the number of Users Stories for a given Sprint PO associated with PO invoices needing correction? Ho = Ha =
Constructing the Hypotheses
> The Hypotheses >> The status quo hypothesis represents what has been tentatively assumed about the value of the parameter and is called the null hypothesis, dnoted as Ho. >> The alternative hypothesis, or research hypothesis, denoted as Ha represents an alternative claim about the value of the parameter.
Number of Unique Projects vs. PO Invoices Approval Within Threshold: -Is the number of unique projects for a given Sprint PO associated with PO invoices not being approved within our threshold time? Ho = Ha =
Number of Unique Projects vs. PO Invoices Needing Correction: -Is the number or unique projects for a given Sprint PO associated with PO invoices needing to be corrected? Ho = Ha =
Statistical hypothesis testing - The explanation of a confidence interval can amount to something like: "The confidence interval represents values for the population parameter for which the difference between the parameter and the observed estimate is not statistically significant at the 10% level".

## Analyze-POInvoiceApprovalCycleT
| Hypothesis Statements | [7 empty] | Hypothesis Outcome | Test Statistic
| PO Invoices not approved within discount threshold: Is my average PO Approval process cycle time (avg = 21 days , std dev = 5.5) performing well versus goal (avg less than 19 days)? Type of Data: Continuous Sample Size: n = 36 Ho = PO Approval Process Cycle Time Avg is greater than 19 days = µ >= 19 days Ha = PO Approval Process Cycle Time Avg is greater than 19 days = µ < 19 days We do not reject the null hypothesis, our PO Approval Process Cycle Time Avg is greather than the given threshold of 19 days | [7 empty] | We do not reject the null hypothesis, our PO Approval Process Cycle Time Avg is greather than the given threshold of 19 days | One-Tail Test Lower/left-tail Sample Size = 36 Test Statistic: Z=xBar-µ / (s/√n) = (21-19) / (5.5/6) = 2 / .92 = 2.17 = .9850 p = 0.838
| PO Approval Cycle Time (days) | Bins | [7 empty] | p-value = | 0.83769
PO ID
PO1 | 29 | 19 | PO Approval Cycle Time |  | Bin | Frequency
PO2 | 30 | 40 |  |  | 19 | 7
PO3 | 30 |  | Mean | 21.1389 | 40 | 29
PO4 | 24 |  | Standard Error | 0.91734 | More | 0
PO5 | 23 |  | Median | 22
PO6 | 24 |  | Mode | 24
PO7 | 23 |  | Standard Deviation | 5.504
PO8 | 23 |  | Sample Variance | 30.2944
PO9 | 20 |  | Kurtosis | 0.80291
PO10 | 20 |  | Skewness | -0.93054
PO11 | 20 |  | Range | 23
PO12 | 20 |  | Minimum | 7
PO13 | 24 |  | Maximum | 30
PO14 | 20 |  | Sum | 761
PO15 | 24 |  | Count | 36
PO16 | 20
PO17 | 24 | [5 empty] | Bin | Frequency
PO18 | 10 | [5 empty] | 7 | 1
PO19 | 21 | [5 empty] | 10.8333 | 3
PO20 | 21 | [5 empty] | 14.6667 | 1
PO21 | 17 | [5 empty] | 18.5 | 2
PO22 | 21 | [5 empty] | 22.3333 | 11
PO23 | 21 | [5 empty] | 26.1667 | 13
PO24 | 24 | [5 empty] | More | 5
PO25 | 21
PO26 | 24
PO27 | 13
PO28 | 24
PO29 | 10
PO30 | 10
PO31 | 24
PO32 | 17
PO33 | 27
PO34 | 24
PO35 | 27
PO36 | 7
This chart isn't available in your version of Excel. Editing this shape or saving this workbook into a different file format will permanently break the chart.

## Analyze-CorrectionVsWithinThrsh
|  | Hypothesis Statements |  |  | Hypothesis Outcome |  |  |  |  | Data Characteristics
|  | PO Invoices needing correction: Is my PO Invoice Type of Data: Sample Size: n = 36 Ho = = µ <= 20% Ha = = µ > 20% Ho: | [7 empty] | >>> Is a Discrete Categorical attribute >>> Test for Independence, Chi-Squared >>> Ho: Variable A and Variable B are independent >>> Ha: Variable A and Variable B are dependent
PO ID | Needed Correction (Y/N) | Within Disc Threshold (Y/N) | Class |  | 1 | Yes Correction | No Correction | % Corrected | % Not Corrected
PO1 | Y | N | 1 |  |  | 25 | 11 | 69.44% | 30.56%
PO2 | Y | N | 1
PO3 | Y | N | 1
PO4 | Y | N | 1
PO5 | Y | N | 1
PO6 | Y | N | 1
PO7 | Y | N | 1
PO8 | N | N | 0
PO9 | Y | N | 1
PO10 | Y | N | 1
PO11 | Y | N | 1
PO12 | N | N | 0
PO13 | Y | N | 1
PO14 | Y | N | 1
PO15 | Y | N | 1
PO16 | Y | N | 1
PO17 | Y | N | 1
PO18 | N | N | 0
PO19 | Y | N | 1
PO20 | Y | N | 1
PO21 | N | N | 0
PO22 | Y | N | 1
PO23 | N | N | 0
PO24 | Y | N | 1
PO25 | Y | N | 1
PO26 | N | N | 0
PO27 | N | N | 0
PO28 | Y | N | 1
PO29 | N | N | 0
PO30 | N | N | 0
PO31 | Y | N | 1
PO32 | N | N | 0
PO33 | Y | N | 1
PO34 | Y | N | 1
PO35 | Y | N | 1
PO36 | N | N | 0
Count = | 36 |  | 25 | 0.69444

## Analyze-POInvoiceCorrectionFrq
|  | Hypothesis Statements |  |  |  |  | Hypothesis Outcome | Data Characteristics
|  | PO Invoices needing correction: Is my PO Invoice that need correction ratio () performing well versus goal (20% or less of PO Invoices needing to be corrected after submission in Ariba procurment system)? Type of Data: Discrete, Is it Binomial Distrobution? Sample Size: n = 36 Ho = Our current PO Invoice Correction frequency is 20% or less = µ <= 20% Ha = Our current PO Invoice Correction frequency is greater than 20% = µ > 20% Ho: p <= p0 = 20% <= 69.4% |  |  |  |  | >> Discrete > One Sample >> Upper/right-tail >> Test Statistic >>> Z = p-p0/√p0(1-p0)/n = .20-.694 >>> Z = -6.432 >>> p-value = 1 | >>> Is a Discrete Categorical attribute >>>
PO ID | Needed Correction (Y/N) |  | Yes Correction | No Correction | % Corrected | % Not Corrected | 1
PO1 | Y |  | 25 | 11 | 69.44% | 30.56%
PO2 | Y
PO3 | Y
PO4 | Y
PO5 | Y
PO6 | Y
PO7 | Y
PO8 | N
PO9 | Y
PO10 | Y
PO11 | Y
PO12 | N
PO13 | Y
PO14 | Y
PO15 | Y
PO16 | Y
PO17 | Y
PO18 | N
PO19 | Y
PO20 | Y
PO21 | N
PO22 | Y
PO23 | N
PO24 | Y
PO25 | Y
PO26 | N
PO27 | N
PO28 | Y
PO29 | N
PO30 | N
PO31 | Y
PO32 | N
PO33 | Y
PO34 | Y
PO35 | Y
PO36 | N
Count = | 36

## Analyze-DevMgrCycleTime
|  | Hypothesis Statements | [11 empty] | Hypothesis Outcome | Data Characteristics
|  | Dev Manager Validation Cycle Time: -Is my average dev manager validation process time (avg = , std dev = , ) performing well versus our goal (avg less than or equal to 2 hrs)? Type of Data: Continuous, One Sample Sample Size: n = 36 Ho = Mgr Validation Process Cycle Time Avg is less than or equal to 2 hrs = µ <= 2 hrs Ha = Mgr Validation Process Cycle Time Avg is greater than 2 hrs = µ > 2 hrs Data is | [11 empty] | >> | >>> Continuous, Time >>>
PO ID | Mgr Validation Time (hrs) | Threshold | Above Threshold | Below Threshold
PO1 | 3 | 2 | 24 | 12 | Mgr Validation Cycle Time
PO2 | 4 | 2
PO3 | 2 | 2 | % Above Threshold | % Below Threshold | Mean | 2.9167
PO4 | 3 | 2 | 66.67% | 33.33% | Standard Error | 0.19262
PO5 | 3 | 2 |  |  | Median | 3
PO6 | 2 | 2 |  |  | Mode | 3
PO7 | 4 | 2 |  |  | Standard Deviation | 1.1557
PO8 | 3 | 2 |  |  | Sample Variance | 1.3357
PO9 | 3 | 2 |  |  | Kurtosis | -0.61468
PO10 | 3 | 2 |  |  | Skewness | -0.064506
PO11 | 3 | 2 |  |  | Range | 4
PO12 | 3 | 2 |  |  | Minimum | 1
PO13 | 3 | 2 |  |  | Maximum | 5
PO14 | 4 | 2 |  |  | Sum | 105
PO15 | 2 | 2 |  |  | Count | 36
PO16 | 4 | 2 |  |  | Confidence Level(95.0%) | 0.39104
PO17 | 4 | 2
PO18 | 1 | 2
PO19 | 4 | 2
PO20 | 4 | 2 |  |  |  | Mgr Validation Cycle Time
PO21 | 1 | 2
PO22 | 4 | 2 |  |  |  | Mean | 2.9167
PO23 | 3 | 2 |  |  |  | Standard Error | 0.19262
PO24 | 2 | 2 |  |  |  | Median | 3
PO25 | 5 | 2 |  |  |  | Standard Deviation | 1.1557
PO26 | 3 | 2 |  |  |  | Sample Variance | 1.3357
PO27 | 1 | 2 |  |  |  | Range | 4
PO28 | 5 | 2 |  |  |  | Minimum | 1
PO29 | 2 | 2 |  |  |  | Maximum | 5
PO30 | 1 | 2 |  |  |  | Count | 36
PO31 | 5 | 2
PO32 | 2 | 2
PO33 | 1 | 2
PO34 | 3 | 2 |  |  |  | % Above Threshold | % Below Threshold
PO35 | 3 | 2
PO36 | 2 | 2
PO ID | Mgr Validation Time (hrs) | Threshold | Above Threshold | Below Threshold
PO40 | 1 | 2 | 0 | 15 | Mgr Validation Time (hrs) |  |  | Bin | Frequency | Cumulative % | Bin | Frequency | Cumulative %
PO41 | 1 | 2 | [5 empty] | 0.25 | 3 | 20% | 1.4167 | 7 | 46.67%
PO42 | 0.5 | 2 | % Above Threshold | % Below Threshold | Mean | 0.85 |  | 0.83333 | 3 | 40% | 0.25 | 3 | 66.67%
PO43 | 1 | 2 | 0% | 100% | Standard Error | 0.1263 |  | 1.4167 | 7 | 86.67% | 0.83333 | 3 | 86.67%
PO44 | 0.5 | 2 |  |  | Standard Deviation | 0.48917 |  | More | 2 | 100% | More | 2 | 100%
PO45 | 1.5 | 2 |  |  | Sample Variance | 0.23929
PO46 | 1 | 2 |  |  | Range | 1.75
PO47 | 0.5 | 2 |  |  | Minimum | 0.25
PO48 | 0.25 | 2 |  |  | Maximum | 2
PO49 | 1 | 2 |  |  | Count | 15
PO50 | 2 | 2
PO51 | 0.25 | 2
PO52 | 1 | 2
PO53 | 1 | 2
PO54 | 0.25 | 2

## Analyze-DevTeamCycleTime
|  | Hypothesis Statements |  |  |  |  | Hypothesis Outcome | Data Characteristics
|  | Dev Team PO Validation Cycle Time: -Is my average dev team PO validation process cycle time (avg = , std dev = ) performing well versus our goal (avg less than or equal to 3 hrs)? Type of Data: Continuous, One Sample Sample Size: n = 36 Ho = DevTeam Validation Process Cycle Time Avg is less than or equal to 3 hrs = µ <= 3 hrs Ha = DevTeam Validation Process Cycle Time Avg is greater than 3 hrs = µ > 3 hrs Data is | [5 empty] | >>> Continuous, Time >>>
PO ID | Team Validation Meetings Time (hrs) | Threshold | Above Threshold | Below Threshold
PO1 | 3 | 3 | 13 | 23 | Team Validation Cycyle Time
PO2 | 4 | 3
PO3 | 3 | 3 | % Above Threshold | % Below Threshold | Mean | 2.5417
PO4 | 4 | 3 | 36.11% | 63.89% | Standard Error | 0.22127
PO5 | 4 | 3 |  |  | Median | 3
PO6 | 3 | 3 |  |  | Mode | 4
PO7 | 4 | 3 |  |  | Standard Deviation | 1.3276
PO8 | 1 | 3 |  |  | Sample Variance | 1.7625
PO9 | 1 | 3 |  |  | Range | 3
PO10 | 3 | 3 |  |  | Minimum | 1
PO11 | 3 | 3 |  |  | Maximum | 4
PO12 | 1.5 | 3 |  |  | Count | 36
PO13 | 3 | 3
PO14 | 4 | 3
PO15 | 1 | 3
PO16 | 3 | 3
PO17 | 4 | 3
PO18 | 1 | 3
PO19 | 4 | 3
PO20 | 4 | 3
PO21 | 1 | 3
PO22 | 4 | 3
PO23 | 1 | 3
PO24 | 1 | 3
PO25 | 4 | 3
PO26 | 1 | 3
PO27 | 1 | 3
PO28 | 4 | 3
PO29 | 1 | 3
PO30 | 1 | 3
PO31 | 4 | 3
PO32 | 1 | 3
PO33 | 2 | 3
PO34 | 4 | 3
PO35 | 2 | 3
PO36 | 1 | 3

## Analyze-ValidationCyTVsApprova
|  | Hypothesis Statements | [7 empty] | Hypothesis Outcome | [6 empty] | Data Characteristics
|  | PO Invoice Validation Time vs. PO Invoice Approval Time Within Threshold: -Is PO invoice validation time associated with PO invoices not being approved within our threshold time? Type of Data: Sample Size: n = 36 Ho = Having to correct a PO Invoice after submission has no impact on a PO being approved within our threshold time = µ <= Ha = = µ > 20% Ho: | [14 empty] | >>> Is a Discrete Categorical attribute >>>
PO ID | PO Approval Cycle Time (days) | Mgr Validation Time (hrs) | Team Validation Meetings Time (hrs) | Correlation Analysis |  |  |  |  | PO Approval Cycle Time (Y) / Mgr Validation Cycle Time (X)
PO1 | 29 | 3 | 3 |  | PO Approval Cycle Time (days) | Mgr Validation Time (hrs) | Team Validation Meetings Time (hrs) |  | SUMMARY OUTPUT
PO2 | 30 | 4 | 4 | PO Approval Cycle Time (days) | 1
PO3 | 30 | 2 | 3 | Mgr Validation Time (hrs) | 0.4106 | 1 |  |  | Regression Statistics
PO4 | 24 | 3 | 4 | Team Validation Meetings Time (hrs) | 0.48795 | 0.73787 | 1 |  | Multiple R | 0.4106
PO5 | 23 | 3 | 4 | [5 empty] | R Square | 0.16859 | <<
PO6 | 24 | 2 | 3 | [5 empty] | Adjusted R Square | 0.14414
PO7 | 23 | 4 | 4 | [5 empty] | Standard Error | 5.0919
PO8 | 23 | 3 | 1 | [5 empty] | Observations | 36
PO9 | 20 | 3 | 1
PO10 | 20 | 3 | 3 | [5 empty] | ANOVA
PO11 | 20 | 3 | 3 | [6 empty] | df | SS | MS | F | Significance F
PO12 | 20 | 3 | 1.5 | [5 empty] | Regression | 1 | 178.7595 | 178.7595 | 6.8945 | 0.012866
PO13 | 24 | 3 | 3 | [5 empty] | Residual | 34 | 881.546 | 25.9278
PO14 | 20 | 4 | 4 | [5 empty] | Total | 35 | 1060.3056
PO15 | 24 | 2 | 1
PO16 | 20 | 4 | 3 | [6 empty] | Coefficients | Standard Error | t Stat | P-value | Lower 95% | Upper 95% | Lower 95.0% | Upper 95.0%
PO17 | 24 | 4 | 4 | [5 empty] | Intercept | 15.4355 | 2.332 | 6.619 | 1.3684e-07 | 10.6963 | 20.1747 | 10.6963 | 20.1747
PO18 | 10 | 1 | 1 |  |  |  |  | slope>> | X Variable 1 | 1.9554 | 0.74472 | 2.6257 | 0.012866 | 0.44199 | 3.4689 | 0.44199 | 3.4689
PO19 | 21 | 4 | 4
PO20 | 21 | 4 | 4 | [5 empty] | PO Approval Cycle Time (Y) / Team Validation Cycle Time (X)
PO21 | 17 | 1 | 1 | [5 empty] | SUMMARY OUTPUT
PO22 | 21 | 4 | 4
PO23 | 21 | 3 | 1 | [5 empty] | Regression Statistics
PO24 | 24 | 2 | 1 | [5 empty] | Multiple R | 0.48795
PO25 | 21 | 5 | 4 | [5 empty] | R Square | 0.23809
PO26 | 24 | 3 | 1 | [5 empty] | Adjusted R Square | 0.21568
PO27 | 13 | 1 | 1 | [5 empty] | Standard Error | 4.8745
PO28 | 24 | 5 | 4 | [5 empty] | Observations | 36
PO29 | 10 | 2 | 1
PO30 | 10 | 1 | 1 | [5 empty] | ANOVA
PO31 | 24 | 5 | 4 | [6 empty] | df | SS | MS | F | Significance F
PO32 | 17 | 2 | 1 | [5 empty] | Regression | 1 | 252.4492 | 252.4492 | 10.6248 | 0.002537
PO33 | 27 | 1 | 2 | [5 empty] | Residual | 34 | 807.8564 | 23.7605
PO34 | 24 | 3 | 4 | [5 empty] | Total | 35 | 1060.3056
PO35 | 27 | 3 | 2
PO36 | 7 | 2 | 1 | [6 empty] | Coefficients | Standard Error | t Stat | P-value | Lower 95% | Upper 95% | Lower 95.0% | Upper 95.0%
[9 empty] | Intercept | 15.9972 | 1.7743 | 9.0159 | 1.545e-10 | 12.3913 | 19.6031 | 12.3913 | 19.6031
[8 empty] | slope>> | X Variable 1 | 2.023 | 0.62062 | 3.2596 | 0.002537 | 0.7617 | 3.2842 | 0.7617 | 3.2842
[9 empty] | Slope |  |  | Intercept
[9 empty] | Standard Error of Slope |  |  | Standard Error of Intercept
[9 empty] | r2 |  |  | Standard Error of Estimate
[9 empty] | F |  |  | degrees of freedom
[9 empty] | Sum of Squares Regression |  |  | Sum of Squares Residual

## Analyze-CorrectionVsApprovalCyT
|  | Hypothesis Statements |  |  |  | Hypothesis Outcome | Data Characteristics
|  | PO Invoice Needing Correction vs. PO Invoice Approval Within Threshold: -Is PO invoice needed correction associated with PO invoices not being approved within our threshold time? Type of Data: Sample Size: n = 36 Ho = Having to correct a PO Invoice after submission has no impact on a PO being approved within our threshold time = µ <= Ha = = µ > 20% Ho: |  |  |  |  | >>> Is a Discrete Categorical attribute >>>
PO ID | PO Approval Cycle Time (days) | Needed Correction (Y/N) |  | Yes | No
PO1 | 29 | Y |  | 29
PO2 | 30 | Y |  | 30
PO3 | 30 | Y |  | 30
PO4 | 24 | Y |  | 24
PO5 | 23 | Y |  | 23
PO6 | 24 | Y |  | 24
PO7 | 23 | Y |  | 23
PO8 | 23 | N |  |  | 23
PO9 | 20 | Y |  | 20
PO10 | 20 | Y |  | 20
PO11 | 20 | Y |  | 20
PO12 | 20 | N |  |  | 20
PO13 | 24 | Y |  | 24
PO14 | 20 | Y |  | 20
PO15 | 24 | Y |  | 24
PO16 | 20 | Y |  | 20
PO17 | 24 | Y |  | 24
PO18 | 10 | N |  |  | 10
PO19 | 21 | Y |  | 21
PO20 | 21 | Y |  | 21
PO21 | 17 | N |  |  | 17
PO22 | 21 | Y |  | 21
PO23 | 21 | N |  |  | 21
PO24 | 24 | Y |  | 24
PO25 | 21 | Y |  | 21
PO26 | 24 | N |  |  | 24
PO27 | 13 | N |  |  | 13
PO28 | 24 | Y |  | 24
PO29 | 10 | N |  |  | 10
PO30 | 10 | N |  |  | 10
PO31 | 24 | Y |  | 24
PO32 | 17 | N |  |  | 17
PO33 | 27 | Y |  | 27
PO34 | 24 | Y |  | 24
PO35 | 27 | Y |  | 27
PO36 | 7 | N |  |  | 7
|  |  | avg | 23.56 | 15.6364
|  |  | std dev | 3.021 | 5.6612
rang

## Analyze-UserStoryVsApprovalCyT
|  | Hypothesis Statements | [6 empty] | Hypothesis Outcome | Data Characteristics
|  | Number of User Stories vs. PO Invoice Approval Within Threshold: -Is the number of User Stories for a given Sprint PO associated with PO invoices not being approved withn our threshold time? Sample Size: n = 36 Ho = PO Approval Cycle Time is not effected by the number of User Stories in the given PO Invoice Ha = PO Approval Cycle Time is effected by the number of User Stories in the given PO Invoice >>> p-value is lower than our confidence alpha of .05, we reject the Null Hypothesis >>> PO Approval Cycle Time is effected by the number of Users Stories in the given PO Invoice. The linear trend line shows a positive increase. | [7 empty] | >>> Is a Discrete Categorical attribute >>>
PO ID | PO Approval Cycle Time (days) | User Stories Count
PO1 | 29 | 10
PO2 | 30 | 15
PO3 | 30 | 8
PO4 | 24 | 14
PO5 | 23 | 15
PO6 | 24 | 6
PO7 | 23 | 15
PO8 | 23 | 15
PO9 | 20 | 10
PO10 | 20 | 11
PO11 | 20 | 11
PO12 | 20 | 13
PO13 | 24 | 8
PO14 | 20 | 13
PO15 | 24 | 8
PO16 | 20 | 9
PO17 | 24 | 11
PO18 | 10 | 6
PO19 | 21 | 10
PO20 | 21 | 11
PO21 | 17 | 5
PO22 | 21 | 10
PO23 | 21 | 11
PO24 | 24 | 7
PO25 | 21 | 14
PO26 | 24 | 10
PO27 | 13 | 5
PO28 | 24 | 15
PO29 | 10 | 4
PO30 | 10 | 5
PO31 | 24 | 15
PO32 | 17 | 6
PO33 | 27 | 6
PO34 | 24 | 9
PO35 | 27 | 7
PO36 | 7 | 8
SUMMARY OUTPUT
Regression Statistics
Multiple R | 0.4317
R Square | 0.18636
Adjusted R Square | 0.16243
Standard Error | 5.0372
Observations | 36
ANOVA
| df | SS | MS | F | Significance F
Regression | 1 | 197.6007 | 197.6007 | 7.7876 | 0.008564
Residual | 34 | 862.7048 | 25.3737
Total | 35 | 1060.3056
| Coefficients | Standard Error | t Stat | P-value | Lower 95% | Upper 95% | Lower 95.0% | Upper 95.0%
Intercept | 14.3198 | 2.5838 | 5.5422 | 3.3905e-06 | 9.0689 | 19.5706 | 9.0689 | 19.5706
User Stories Count | 0.68957 | 0.2471 | 2.7906 | 0.008564 | 0.1874 | 1.1917 | 0.1874 | 1.1917
y hat = 14.32 + 0.69x

## Analyze-UserStoryVsCorrection
|  | Hypothesis Statements | [8 empty] | Hypothesis Outcome | [5 empty] | Data Characteristics
|  | Number of User Stories vs. PO Invoice Needing Correction: -Is the number of Users Stories for a given Sprint PO Invoice associated with PO Invoices needing correction? Type of Data: Categorical Sample Size: n = 36 Ho = PO Invoice User Story Count and PO Invoices needing correction are independent (no relationship) Ha = PO Invoice User Story Count and PO Invoices needing correction are not independent (is a relationship) >>> p-value = 0.005587 >>> p is low, Ho must go. Reject Null Hypothesis >>> There is a relationship between the Number of User Stories and PO Invoice needing correction | [8 empty] | >>> p-value = 0.005587 >>> p is low, Ho must go. Reject Null Hypothesis >>> There is a relationship between the Number of User Stories and PO Invoice needing correction | [5 empty] | >>> Is a Discrete Categorical attribute >>> If group data into categories, can use chi-squared test for independence >>> Calculate degrees of freedom (df) df = (r-1) * (c-1) = (2-1) * (3-1) = 1 * 2 = 2 df = 2 | Returns the right-tailed probability of the chi-squared distribution.
[18 empty] | Chi-square | 0.41213 | = CHISQ.DIST.RT(3.955, 4)
[18 empty] | Distribution |  | 3.955 = calculated chi-square value
[18 empty] | (probability) |  | 4 = degrees of freedom = (r-1) x (c-1)
r = number of rows in the two-way table = 3
c = number of columns in the two-way table = 3
Returns the probability for the chi-square test for independence.
[19 empty] | pvalue = | CHISQ.TEST(data range1, data range2)
[6 empty] | Actual (observed) Frequencies | [5 empty] | Expected Frequencies | [7 empty] | data range 1 = observed (actual) values in the two-way table
[6 empty] | PO Invoice User Story Count Groupings | [5 empty] | PO Invoice User Story Count Groupings | [7 empty] | data range 2 = expected (calculated) values in the two-way table
PO ID | User Stories Count | Needed Correction (Y/N) | Low 1-5 | Med 6-10 | High 11-15 | Needed Correction (Y/N) | Low 1-5 | Med 6-10 | High 11-15 | Total |  | Needed Correction (Y/N) | Low 1-5 | Med 6-10 | High 11-15 | Total
PO1 | 10 | Y | 0 | 1 | 0 | No | 4 | 4 | 3 | 11 |  | No | 1.2222 | 4.8889 | 4.8889 | 11
PO2 | 15 | Y | 0 | 0 | 1 | Yes | 0 | 12 | 13 | 25 |  | Yes | 2.7778 | 11.1111 | 11.1111 | 25
PO3 | 8 | Y | 0 | 1 | 0 | Total | 4 | 16 | 16 | 36 |  | Total | 4 | 16 | 16 | 36
PO4 | 14 | Y | 0 | 0 | 1
PO5 | 15 | Y | 0 | 0 | 1 |  |  |  |  | p-value: | 0.0055872
PO6 | 6 | Y | 0 | 1 | 0
PO7 | 15 | Y | 0 | 0 | 1
PO8 | 15 | N | 0 | 0 | 1
PO9 | 10 | Y | 0 | 1 | 0
PO10 | 11 | Y | 0 | 0 | 1
PO11 | 11 | Y | 0 | 0 | 1
PO12 | 13 | N | 0 | 0 | 1
PO13 | 8 | Y | 0 | 1 | 0
PO14 | 13 | Y | 0 | 0 | 1
PO15 | 8 | Y | 0 | 1 | 0
PO16 | 9 | Y | 0 | 1 | 0
PO17 | 11 | Y | 0 | 0 | 1
PO18 | 6 | N | 0 | 1 | 0
PO19 | 10 | Y | 0 | 1 | 0
PO20 | 11 | Y | 0 | 0 | 1
PO21 | 5 | N | 1 | 0 | 0
PO22 | 10 | Y | 0 | 1 | 0
PO23 | 11 | N | 0 | 0 | 1
PO24 | 7 | Y | 0 | 1 | 0
PO25 | 14 | Y | 0 | 0 | 1
PO26 | 10 | N | 0 | 1 | 0
PO27 | 5 | N | 1 | 0 | 0
PO28 | 15 | Y | 0 | 0 | 1
PO29 | 4 | N | 1 | 0 | 0
PO30 | 5 | N | 1 | 0 | 0
PO31 | 15 | Y | 0 | 0 | 1
PO32 | 6 | N | 0 | 1 | 0
PO33 | 6 | Y | 0 | 1 | 0
PO34 | 9 | Y | 0 | 1 | 0
PO35 | 7 | Y | 0 | 1 | 0
PO36 | 8 | N | 0 | 1 | 0

## Analyze-UniquePrjVsApprovalCyT
|  | Hypothesis Statements | [6 empty] | Hypothesis Outcome | Data Characteristics
|  | Number of Unique Projects vs. PO Invoices Approval Within Threshold: -Is the number of unique projects for a given Sprint PO Invoice associated with a higher than average PO Approval Cycle time? Sample Size: n = 36 Ho = The number of Unique Projects for a given PO Invoice has no impact on the PO Approval Cycle Time Ha = The number of Unique Projects for a given PO Invoice has an impact on the PO Approval Cycle Time >>> p-value of 0.1581 is higher than our alpha of .05, we do not reject the Null Hypothesis >>> Though the Linear Regression shows a slight increase trend our R squared, Coefficent of Determination is low representing a poor fit of our data to the regression line | [7 empty] | >>> Is a Discrete Categorical attribute >>>
PO ID | PO Approval Cycle Time (days) | Unique Project Count
PO1 | 29 | 2
PO2 | 30 | 2
PO3 | 30 | 2
PO4 | 24 | 3
PO5 | 23 | 2
PO6 | 24 | 4
PO7 | 23 | 3
PO8 | 23 | 2
PO9 | 20 | 4
PO10 | 20 | 3
PO11 | 20 | 2
PO12 | 20 | 1
PO13 | 24 | 2
PO14 | 20 | 2
PO15 | 24 | 1
PO16 | 20 | 4
PO17 | 24 | 2
PO18 | 10 | 1
PO19 | 21 | 5
PO20 | 21 | 2
PO21 | 17 | 1
PO22 | 21 | 3
PO23 | 21 | 1
PO24 | 24 | 2
PO25 | 21 | 4
PO26 | 24 | 1
PO27 | 13 | 2
PO28 | 24 | 4
PO29 | 10 | 1
PO30 | 10 | 2
PO31 | 24 | 4
PO32 | 17 | 1
PO33 | 27 | 2
PO34 | 24 | 3
PO35 | 27 | 1
PO36 | 7 | 1
SUMMARY OUTPUT
Regression Statistics
Multiple R | 0.24026
R Square | 0.057726
Adjusted R Square | 0.030012
Standard Error | 5.4208
Observations | 36
ANOVA
| df | SS | MS | F | Significance F
Regression | 1 | 61.2073 | 61.2073 | 2.0829 | 0.15811
Residual | 34 | 999.0983 | 29.3852
Total | 35 | 1060.3056
| Coefficients | Standard Error | t Stat | P-value | Lower 95% | Upper 95% | Lower 95.0% | Upper 95.0%
Intercept | 18.4889 | 2.0464 | 9.0351 | 1.4673e-10 | 14.3302 | 22.6476 | 14.3302 | 22.6476
Unique Project Count | 1.1634 | 0.8061 | 1.4432 | 0.15811 | -0.4748 | 2.8016 | -0.4748 | 2.8016

## Analyze-UniquePrjVsCorrection
|  | Hypothesis Statements | [7 empty] | Hypothesis Outcome | [6 empty] | Data Characteristics
|  | Number of Unique Projects vs. PO Invoices Needing Correction: -Is the number or unique projects for a given Sprint PO Invoice associated with PO invoices needing to be corrected? Type of Data: Categorical Sample Size: n = 36 Ho = PO Invoice Unique Project Count and PO Invoices needing correction are independent (no relationship) Ha = PO Invoice Unique Project Count and PO Invoices needing correction are not independent (is a relationship) >>> p-value = 0.019063 >>> alph (confidence level) = .05 >>> p-value (0.019063) is less than alpha (0.05), we reject the Null Hypothesis that these factors are independent. >>> PO Invoice Unique Project Count and PO Invoices needing correction are NOT independent | [7 empty] | >>> p-value = 0.019063 >>> alph (confidence level) = .05 >>> p-value (0.019063) is less than alpha (0.05), we reject the Null Hypothesis that these factors are independent. | [6 empty] | >>> Is a Discrete Categorical attribute >>> If group data into categories, can use chi-squared test for independence >>> Calculate degrees of freedom (df) df = (r-1) * (c-1) = (2-1) * (3-1) = 1 * 2 = 2 df = 2
[6 empty] | Actual (observed) Frequencies | [5 empty] | Expected Frequencies
PO ID | Unique Project Count | Needed Correction (Y/N) | Low 1-2 | Med 3-4 | High 5-6 | PO Invoice Unique Prj Count Groupings | [5 empty] | PO Invoice Unique Prj Count Groupings
PO1 | 2 | Y | 1 | 0 | 0 | Needed Correction (Y/N) | Low 1-2 | Med 3-4 | High 5-6 | Total |  | Needed Correction (Y/N) | Low 1-2 | Med 3-4 | High 5-6 | Total
PO2 | 2 | Y | 1 | 0 | 0 | No | 11 | 0 | 0 | 11 |  | No | 7.3333 | 3.3611 | 0.30556 | 11
PO3 | 2 | Y | 1 | 0 | 0 | Yes | 13 | 11 | 1 | 25 |  | Yes | 16.6667 | 7.6389 | 0.69444 | 25
PO4 | 3 | Y | 0 | 1 | 0 | Total | 24 | 11 | 1 | 36 |  | Total | 24 | 11 | 1 | 36
PO5 | 2 | Y | 1 | 0 | 0
PO6 | 4 | Y | 0 | 1 | 0 |  |  |  |  | p-value: | 0.019063
PO7 | 3 | Y | 0 | 1 | 0
PO8 | 2 | N | 1 | 0 | 0
PO9 | 4 | Y | 0 | 1 | 0
PO10 | 3 | Y | 0 | 1 | 0
PO11 | 2 | Y | 1 | 0 | 0
PO12 | 1 | N | 1 | 0 | 0
PO13 | 2 | Y | 1 | 0 | 0
PO14 | 2 | Y | 1 | 0 | 0
PO15 | 1 | Y | 1 | 0 | 0
PO16 | 4 | Y | 0 | 1 | 0
PO17 | 2 | Y | 1 | 0 | 0
PO18 | 1 | N | 1 | 0 | 0
PO19 | 5 | Y | 0 | 0 | 1
PO20 | 2 | Y | 1 | 0 | 0
PO21 | 1 | N | 1 | 0 | 0
PO22 | 3 | Y | 0 | 1 | 0
PO23 | 1 | N | 1 | 0 | 0
PO24 | 2 | Y | 1 | 0 | 0
PO25 | 4 | Y | 0 | 1 | 0
PO26 | 1 | N | 1 | 0 | 0
PO27 | 2 | N | 1 | 0 | 0
PO28 | 4 | Y | 0 | 1 | 0
PO29 | 1 | N | 1 | 0 | 0
PO30 | 2 | N | 1 | 0 | 0
PO31 | 4 | Y | 0 | 1 | 0
PO32 | 1 | N | 1 | 0 | 0
PO33 | 2 | Y | 1 | 0 | 0
PO34 | 3 | Y | 0 | 1 | 0
PO35 | 1 | Y | 1 | 0 | 0
PO36 | 1 | N | 1 | 0 | 0

## Analyze-HypothesisTesting
Defects
Hypothesis Testing: Means and Proportions | A PO invoice needing correction after submission in Ariaba
A PO invoice not approved in Ariaba within discount threshold time
A Dev Manager spending more than 2 hours to validate and approve a PO invoice
A Dev Team spending more than 3 hours to validate and or correct a PO invoice

## Control
| PO Approval Cycle Time (days) |  |  |  | R-chart |  |  |  |  | x bar chart
|  |  | Calculations>>> |  |  | Centerline
PO ID |  | mR |  |  | mR | Rbar | UCL | LCL | x | x-bar | UCL | LCL | Avg Trade Deficit (x-bar)
PO1 | 29 |  |  |  |  | 4.8 | 15.696 | 0 | 29 | 21.1389 | 33.9069 | 8.3709 | 21.1389
PO2 | 30 | 1 |  |  | 1 | 4.8 | 15.696 | 0 | 30 | 21.1389 | 33.9069 | 8.3709
PO3 | 30 | 0 |  |  | 0 | 4.8 | 15.696 | 0 | 30 | 21.1389 | 33.9069 | 8.3709 | Avg Moving Range (Rbar)
PO4 | 24 | 6 |  |  | 6 | 4.8 | 15.696 | 0 | 24 | 21.1389 | 33.9069 | 8.3709 | 4.8
PO5 | 23 | 1 |  |  | 1 | 4.8 | 15.696 | 0 | 23 | 21.1389 | 33.9069 | 8.3709
PO6 | 24 | 1 |  |  | 1 | 4.8 | 15.696 | 0 | 24 | 21.1389 | 33.9069 | 8.3709 | Natural Process Limits: X Chart
PO7 | 23 | 1 |  |  | 1 | 4.8 | 15.696 | 0 | 23 | 21.1389 | 33.9069 | 8.3709 | UNPL: | 33.9069
PO8 | 23 | 0 |  |  | 0 | 4.8 | 15.696 | 0 | 23 | 21.1389 | 33.9069 | 8.3709 | LNPL: | 8.3709
PO9 | 20 | 3 |  |  | 3 | 4.8 | 15.696 | 0 | 20 | 21.1389 | 33.9069 | 8.3709
PO10 | 20 | 0 |  |  | 0 | 4.8 | 15.696 | 0 | 20 | 21.1389 | 33.9069 | 8.3709 | Upper Control Limit: Range Chart
PO11 | 20 | 0 |  |  | 0 | 4.8 | 15.696 | 0 | 20 | 21.1389 | 33.9069 | 8.3709 | UCL: | 15.696
PO12 | 20 | 0 |  |  | 0 | 4.8 | 15.696 | 0 | 20 | 21.1389 | 33.9069 | 8.3709
PO13 | 24 | 4 |  |  | 4 | 4.8 | 15.696 | 0 | 24 | 21.1389 | 33.9069 | 8.3709
PO14 | 20 | 4 |  |  | 4 | 4.8 | 15.696 | 0 | 20 | 21.1389 | 33.9069 | 8.3709
PO15 | 24 | 4 |  |  | 4 | 4.8 | 15.696 | 0 | 24 | 21.1389 | 33.9069 | 8.3709
PO16 | 20 | 4 |  |  | 4 | 4.8 | 15.696 | 0 | 20 | 21.1389 | 33.9069 | 8.3709
PO17 | 24 | 4 |  |  | 4 | 4.8 | 15.696 | 0 | 24 | 21.1389 | 33.9069 | 8.3709
PO18 | 10 | 14 |  |  | 14 | 4.8 | 15.696 | 0 | 10 | 21.1389 | 33.9069 | 8.3709
PO19 | 21 | 11 |  |  | 11 | 4.8 | 15.696 | 0 | 21 | 21.1389 | 33.9069 | 8.3709
PO20 | 21 | 0 |  |  | 0 | 4.8 | 15.696 | 0 | 21 | 21.1389 | 33.9069 | 8.3709
PO21 | 17 | 4 |  |  | 4 | 4.8 | 15.696 | 0 | 17 | 21.1389 | 33.9069 | 8.3709
PO22 | 21 | 4 |  |  | 4 | 4.8 | 15.696 | 0 | 21 | 21.1389 | 33.9069 | 8.3709
PO23 | 21 | 0 |  |  | 0 | 4.8 | 15.696 | 0 | 21 | 21.1389 | 33.9069 | 8.3709
PO24 | 24 | 3 |  |  | 3 | 4.8 | 15.696 | 0 | 24 | 21.1389 | 33.9069 | 8.3709
PO25 | 21 | 3 |  |  | 3 | 4.8 | 15.696 | 0 | 21 | 21.1389 | 33.9069 | 8.3709
PO26 | 24 | 3 |  |  | 3 | 4.8 | 15.696 | 0 | 24 | 21.1389 | 33.9069 | 8.3709
PO27 | 13 | 11 |  |  | 11 | 4.8 | 15.696 | 0 | 13 | 21.1389 | 33.9069 | 8.3709
PO28 | 24 | 11 |  |  | 11 | 4.8 | 15.696 | 0 | 24 | 21.1389 | 33.9069 | 8.3709
PO29 | 10 | 14 |  |  | 14 | 4.8 | 15.696 | 0 | 10 | 21.1389 | 33.9069 | 8.3709
PO30 | 10 | 0 |  |  | 0 | 4.8 | 15.696 | 0 | 10 | 21.1389 | 33.9069 | 8.3709
PO31 | 24 | 14 |  |  | 14 | 4.8 | 15.696 | 0 | 24 | 21.1389 | 33.9069 | 8.3709
PO32 | 17 | 7 |  |  | 7 | 4.8 | 15.696 | 0 | 17 | 21.1389 | 33.9069 | 8.3709
PO33 | 27 | 10 |  |  | 10 | 4.8 | 15.696 | 0 | 27 | 21.1389 | 33.9069 | 8.3709
PO34 | 24 | 3 |  |  | 3 | 4.8 | 15.696 | 0 | 24 | 21.1389 | 33.9069 | 8.3709
PO35 | 27 | 3 |  |  | 3 | 4.8 | 15.696 | 0 | 27 | 21.1389 | 33.9069 | 8.3709
PO36 | 7 | 20 |  |  | 20 | 4.8 | 15.696 | 0 | 7 | 21.1389 | 33.9069 | 8.3709
Avg | 21.1389 | 4.8 |  | Rbar = | 4.8 |  |  |  | x bar bar=
[5 empty] | R-chart |  |  |  |  | x bar chart
| PO Approval Cycle Time (days) |  | Calculations>>> |  |  | Centerline
PO ID |  | mR |  |  | mR | Rbar | UCL | LCL | x | x-bar | UCL | LCL |  | Avg Trade Deficit (x-bar)
PO40 | 13 |  |  |  |  | 1.7143 | 5.6057 | 0 | 13 | 8.8667 | 13.4267 | 4.3067 |  | 8.8667
PO41 | 13 | 0 |  |  | 0 | 1.7143 | 5.6057 | 0 | 13 | 8.8667 | 13.4267 | 4.3067
PO42 | 13 | 0 |  |  | 0 | 1.7143 | 5.6057 | 0 | 13 | 8.8667 | 13.4267 | 4.3067 |  | Avg Moving Range (Rbar)
PO43 | 10 | 3 |  |  | 3 | 1.7143 | 5.6057 | 0 | 10 | 8.8667 | 13.4267 | 4.3067 |  | 1.7143
PO44 | 10 | 0 |  |  | 0 | 1.7143 | 5.6057 | 0 | 10 | 8.8667 | 13.4267 | 4.3067
PO45 | 13 | 3 |  |  | 3 | 1.7143 | 5.6057 | 0 | 13 | 8.8667 | 13.4267 | 4.3067 |  | Natural Process Limits: X Chart
PO46 | 10 | 3 |  |  | 3 | 1.7143 | 5.6057 | 0 | 10 | 8.8667 | 13.4267 | 4.3067 |  | UNPL: | 13.4267
PO47 | 10 | 0 |  |  | 0 | 1.7143 | 5.6057 | 0 | 10 | 8.8667 | 13.4267 | 4.3067 |  | LNPL: | 4.3067
PO48 | 10 | 0 |  |  | 0 | 1.7143 | 5.6057 | 0 | 10 | 8.8667 | 13.4267 | 4.3067
PO49 | 6 | 4 |  |  | 4 | 1.7143 | 5.6057 | 0 | 6 | 8.8667 | 13.4267 | 4.3067 |  | Upper Control Limit: Range Chart
PO50 | 10 | 4 |  |  | 4 | 1.7143 | 5.6057 | 0 | 10 | 8.8667 | 13.4267 | 4.3067 |  | UCL: | 5.6057
PO51 | 6 | 4 |  |  | 4 | 1.7143 | 5.6057 | 0 | 6 | 8.8667 | 13.4267 | 4.3067
PO52 | 3 | 3 |  |  | 3 | 1.7143 | 5.6057 | 0 | 3 | 8.8667 | 13.4267 | 4.3067
PO53 | 3 | 0 |  |  | 0 | 1.7143 | 5.6057 | 0 | 3 | 8.8667 | 13.4267 | 4.3067
PO54 | 3 | 0 |  |  | 0 | 1.7143 | 5.6057 | 0 | 3 | 8.8667 | 13.4267 | 4.3067
Avg | 8.8667 | 1.7143
|  |  |  | Rbar = | 1.7143 |  |  |  | x bar bar=

## Control (2)
| PO Approval Cycle Time (days) |  |  | R-chart |  |  |  |  | x bar chart
|  |  | Calculations>>> |  | Centerline
PO ID |  | mR |  | mR | Rbar | UCL | LCL | x | x-bar | UCL | LCL | Avg Trade Deficit (x-bar)
PO1 | 29 |  |  |  | 3.96 | 12.9492 | 0 | 29 | 17.5294 | 28.063 | 6.9958 | 17.5294
PO2 | 30 | 1 |  | 1 | 3.96 | 12.9492 | 0 | 30 | 17.5294 | 28.063 | 6.9958
PO3 | 30 | 0 |  | 0 | 3.96 | 12.9492 | 0 | 30 | 17.5294 | 28.063 | 6.9958 | Avg Moving Range (Rbar)
PO4 | 24 | 6 |  | 6 | 3.96 | 12.9492 | 0 | 24 | 17.5294 | 28.063 | 6.9958 | 3.96
PO5 | 23 | 1 |  | 1 | 3.96 | 12.9492 | 0 | 23 | 17.5294 | 28.063 | 6.9958
PO6 | 24 | 1 |  | 1 | 3.96 | 12.9492 | 0 | 24 | 17.5294 | 28.063 | 6.9958 | Natural Process Limits: X Chart
PO7 | 23 | 1 |  | 1 | 3.96 | 12.9492 | 0 | 23 | 17.5294 | 28.063 | 6.9958 | UNPL: | 28.063
PO8 | 23 | 0 |  | 0 | 3.96 | 12.9492 | 0 | 23 | 17.5294 | 28.063 | 6.9958 | LNPL: | 6.9958
PO9 | 20 | 3 |  | 3 | 3.96 | 12.9492 | 0 | 20 | 17.5294 | 28.063 | 6.9958
PO10 | 20 | 0 |  | 0 | 3.96 | 12.9492 | 0 | 20 | 17.5294 | 28.063 | 6.9958 | Upper Control Limit: Range Chart
PO11 | 20 | 0 |  | 0 | 3.96 | 12.9492 | 0 | 20 | 17.5294 | 28.063 | 6.9958 | UCL: | 12.9492
PO12 | 20 | 0 |  | 0 | 3.96 | 12.9492 | 0 | 20 | 17.5294 | 28.063 | 6.9958
PO13 | 24 | 4 |  | 4 | 3.96 | 12.9492 | 0 | 24 | 17.5294 | 28.063 | 6.9958
PO14 | 20 | 4 |  | 4 | 3.96 | 12.9492 | 0 | 20 | 17.5294 | 28.063 | 6.9958
PO15 | 24 | 4 |  | 4 | 3.96 | 12.9492 | 0 | 24 | 17.5294 | 28.063 | 6.9958
PO16 | 20 | 4 |  | 4 | 3.96 | 12.9492 | 0 | 20 | 17.5294 | 28.063 | 6.9958
PO17 | 24 | 4 |  | 4 | 3.96 | 12.9492 | 0 | 24 | 17.5294 | 28.063 | 6.9958
PO18 | 10 | 14 |  | 14 | 3.96 | 12.9492 | 0 | 10 | 17.5294 | 28.063 | 6.9958
PO19 | 21 | 11 |  | 11 | 3.96 | 12.9492 | 0 | 21 | 17.5294 | 28.063 | 6.9958
PO20 | 21 | 0 |  | 0 | 3.96 | 12.9492 | 0 | 21 | 17.5294 | 28.063 | 6.9958
PO21 | 17 | 4 |  | 4 | 3.96 | 12.9492 | 0 | 17 | 17.5294 | 28.063 | 6.9958
PO22 | 21 | 4 |  | 4 | 3.96 | 12.9492 | 0 | 21 | 17.5294 | 28.063 | 6.9958
PO23 | 21 | 0 |  | 0 | 3.96 | 12.9492 | 0 | 21 | 17.5294 | 28.063 | 6.9958
PO24 | 24 | 3 |  | 3 | 3.96 | 12.9492 | 0 | 24 | 17.5294 | 28.063 | 6.9958
PO25 | 21 | 3 |  | 3 | 3.96 | 12.9492 | 0 | 21 | 17.5294 | 28.063 | 6.9958
PO26 | 24 | 3 |  | 3 | 3.96 | 12.9492 | 0 | 24 | 17.5294 | 28.063 | 6.9958
PO27 | 13 | 11 |  | 11 | 3.96 | 12.9492 | 0 | 13 | 17.5294 | 28.063 | 6.9958
PO28 | 24 | 11 |  | 11 | 3.96 | 12.9492 | 0 | 24 | 17.5294 | 28.063 | 6.9958
PO29 | 10 | 14 |  | 14 | 3.96 | 12.9492 | 0 | 10 | 17.5294 | 28.063 | 6.9958
PO30 | 10 | 0 |  | 0 | 3.96 | 12.9492 | 0 | 10 | 17.5294 | 28.063 | 6.9958
PO31 | 24 | 14 |  | 14 | 3.96 | 12.9492 | 0 | 24 | 17.5294 | 28.063 | 6.9958
PO32 | 17 | 7 |  | 7 | 3.96 | 12.9492 | 0 | 17 | 17.5294 | 28.063 | 6.9958
PO33 | 27 | 10 |  | 10 | 3.96 | 12.9492 | 0 | 27 | 17.5294 | 28.063 | 6.9958
PO34 | 24 | 3 |  | 3 | 3.96 | 12.9492 | 0 | 24 | 17.5294 | 28.063 | 6.9958
PO35 | 27 | 3 |  | 3 | 3.96 | 12.9492 | 0 | 27 | 17.5294 | 28.063 | 6.9958
PO36 | 7 | 20 |  | 20 | 3.96 | 12.9492 | 0 | 7 | 17.5294 | 28.063 | 6.9958
PO40 | 13 | 6 |  | 6 | 3.96 | 12.9492 | 0 | 13 | 17.5294 | 28.063 | 6.9958
PO41 | 13 | 0 |  | 0 | 3.96 | 12.9492 | 0 | 13 | 17.5294 | 28.063 | 6.9958
PO42 | 13 | 0 |  | 0 | 3.96 | 12.9492 | 0 | 13 | 17.5294 | 28.063 | 6.9958
PO43 | 10 | 3 |  | 3 | 3.96 | 12.9492 | 0 | 10 | 17.5294 | 28.063 | 6.9958
PO44 | 10 | 0 |  | 0 | 3.96 | 12.9492 | 0 | 10 | 17.5294 | 28.063 | 6.9958
PO45 | 13 | 3 |  | 3 | 3.96 | 12.9492 | 0 | 13 | 17.5294 | 28.063 | 6.9958
PO46 | 10 | 3 |  | 3 | 3.96 | 12.9492 | 0 | 10 | 17.5294 | 28.063 | 6.9958
PO47 | 10 | 0 |  | 0 | 3.96 | 12.9492 | 0 | 10 | 17.5294 | 28.063 | 6.9958
PO48 | 10 | 0 |  | 0 | 3.96 | 12.9492 | 0 | 10 | 17.5294 | 28.063 | 6.9958
PO49 | 6 | 4 |  | 4 | 3.96 | 12.9492 | 0 | 6 | 17.5294 | 28.063 | 6.9958
PO50 | 10 | 4 |  | 4 | 3.96 | 12.9492 | 0 | 10 | 17.5294 | 28.063 | 6.9958
PO51 | 6 | 4 |  | 4 | 3.96 | 12.9492 | 0 | 6 | 17.5294 | 28.063 | 6.9958
PO52 | 3 | 3 |  | 3 | 3.96 | 12.9492 | 0 | 3 | 17.5294 | 28.063 | 6.9958
PO53 | 3 | 0 |  | 0 | 3.96 | 12.9492 | 0 | 3 | 17.5294 | 28.063 | 6.9958
PO54 | 3 | 0 |  | 0 | 3.96 | 12.9492 | 0 | 3 | 17.5294 | 28.063 | 6.9958
avg | 17.5294 | 3.96

## timeseries_questions
The next tab of this Excel spreadsheet contains the NFL raw data for these problems.
In the National Football League, the philosophy for winning (rushing, passing, defense) seems to go through cycles. Consider a time series of the average number of rushing yards in the NFL per regular season from 1980 to 2008.
1) Make a time series plot. Is there evidence that the average rushing yards is trending in one direction? Describe the general movement of the series.
2) Fit a first order autoregressive model [AR(1)] using y(t) as the response variable and y (t-1) as the input variable. Record the regression equation.
3) Based on the AR(1) model, forecast the average number of rushing yards in the NFL for the 2009 regular season.
4) Calculate the exponential smoothing models using Excel damping factors 0.8 and 0.2 For each of the exponential smoothing models forecast the average number of rushing yards in the NFL for the 2009 season.
5) Calculate a moving average model using k=5 (Excel interval). Forecast the average number of rushing yards in the NFL for the 2009 season.
Data Source: The Practice of Statistics for Business and Economics 3rd edition, Moore, McCabe, Alwan, Craig, Duckworth

## data
NFL data
| Year (x) | Rushing yards/Game (y)
1 | 1980 | 127.5
2 | 1981 | 130.1
3 | 1982 | 117.8
4 | 1983 | 129.7
5 | 1984 | 123.9
6 | 1985 | 124.9
7 | 1986 | 118.7
8 | 1987 | 123.9
9 | 1988 | 121.4
10 | 1989 | 115.3
11 | 1990 | 113.9
12 | 1991 | 107.7
13 | 1992 | 110.5
14 | 1993 | 110
15 | 1994 | 104.3
16 | 1995 | 108.1
17 | 1996 | 109
18 | 1997 | 113
19 | 1998 | 112.7
20 | 1999 | 106.5
21 | 2000 | 112.6
22 | 2001 | 111.8
23 | 2002 | 116.1
24 | 2003 | 117.9
25 | 2004 | 116.6
26 | 2005 | 112.5
27 | 2006 | 117.3
28 | 2007 | 110.9
29 | 2008 | 114.6
30

## A1
1) Make a time series plot. Is there evidence that the average rushing yards is trending in one direction? Describe the general movement of the series.
| Year (x) | Rushing yards/Game (y)
1 | 1980 | 127.5
2 | 1981 | 130.1
3 | 1982 | 117.8
4 | 1983 | 129.7
5 | 1984 | 123.9
6 | 1985 | 124.9
7 | 1986 | 118.7
8 | 1987 | 123.9
9 | 1988 | 121.4
10 | 1989 | 115.3
11 | 1990 | 113.9
12 | 1991 | 107.7
13 | 1992 | 110.5
14 | 1993 | 110
15 | 1994 | 104.3
16 | 1995 | 108.1
17 | 1996 | 109 | The avg rushing yards per game, from 1980 to 2008, has a negative linear trend. The avg rushing yards per year shows random positive and negative fluxuations year over year, but with an overall negative linear trend.
18 | 1997 | 113
19 | 1998 | 112.7
20 | 1999 | 106.5
21 | 2000 | 112.6
22 | 2001 | 111.8
23 | 2002 | 116.1
24 | 2003 | 117.9
25 | 2004 | 116.6
26 | 2005 | 112.5
27 | 2006 | 117.3
28 | 2007 | 110.9
29 | 2008 | 114.6
30

## A2
2) Fit a first order autoregressive model [AR(1)] using y(t) as the response variable and y (t-1) as the input variable. Record the regression equation.
(this is Yt-1)
|  | output(y) | (x)
| Year (x) | Rushing yards/Game (y) | Lagged output | SUMMARY OUTPUT
1 | 1980 | 127.5
2 | 1981 | 130.1 | 127.5 | Regression Statistics
3 | 1982 | 117.8 | 130.1 | Multiple R | 0.70684
4 | 1983 | 129.7 | 117.8 | R Square | 0.49962
5 | 1984 | 123.9 | 129.7 | Adjusted R Square | 0.48037
6 | 1985 | 124.9 | 123.9 | Standard Error | 4.7943
7 | 1986 | 118.7 | 124.9 | Observations | 28
8 | 1987 | 123.9 | 118.7
9 | 1988 | 121.4 | 123.9 | ANOVA
10 | 1989 | 115.3 | 121.4 |  | df | SS | MS | F | Significance F
11 | 1990 | 113.9 | 115.3 | Regression | 1 | 596.6932 | 596.6932 | 25.9602 | 2.615e-05
12 | 1991 | 107.7 | 113.9 | Residual | 26 | 597.6078 | 22.9849
13 | 1992 | 110.5 | 107.7 | Total | 27 | 1194.3011
14 | 1993 | 110 | 110.5
15 | 1994 | 104.3 | 110 |  | Coefficients | Standard Error | t Stat | P-value | Lower 95% | Upper 95% | Lower 95.0% | Upper 95.0%
16 | 1995 | 108.1 | 104.3 | Intercept | 37.9084 | 15.2395 | 2.4875 | 0.019603 | 6.5832 | 69.2335 | 6.5832 | 69.2335
17 | 1996 | 109 | 108.1 | X Variable 1 | 0.66889 | 0.13128 | 5.0951 | 2.615e-05 | 0.39904 | 0.93873 | 0.39904 | 0.93873
18 | 1997 | 113 | 109
19 | 1998 | 112.7 | 113 | Regression Equation:
20 | 1999 | 106.5 | 112.7 | 0.66888x + 37.908 = y predicted = y hat
21 | 2000 | 112.6 | 106.5
22 | 2001 | 111.8 | 112.6 | Forecast 2009 using 2008 data as the input for x:
23 | 2002 | 116.1 | 111.8 | 114.5626
24 | 2003 | 117.9 | 116.1
25 | 2004 | 116.6 | 117.9
26 | 2005 | 112.5 | 116.6
27 | 2006 | 117.3 | 112.5
28 | 2007 | 110.9 | 117.3
29 | 2008 | 114.6 | 110.9
30 |  |  | 114.6

## A3
3) Based on the AR(1) model, forecast the average number of rushing yards in the NFL for the 2009 regular season.
output(y)
| Year (x) | Rushing yards/Game (y) | Regression Equation:
1 | 1980 | 127.5 | 0.66888x + 37.908 = y predicted = y hat
2 | 1981 | 130.1
3 | 1982 | 117.8 | Forecast 2009 using 2008 data as the input for x:
4 | 1983 | 129.7 | 114.5616
5 | 1984 | 123.9
6 | 1985 | 124.9
7 | 1986 | 118.7
8 | 1987 | 123.9
9 | 1988 | 121.4
10 | 1989 | 115.3
11 | 1990 | 113.9
12 | 1991 | 107.7
13 | 1992 | 110.5
14 | 1993 | 110
15 | 1994 | 104.3
16 | 1995 | 108.1
17 | 1996 | 109
18 | 1997 | 113
19 | 1998 | 112.7
20 | 1999 | 106.5
21 | 2000 | 112.6
22 | 2001 | 111.8
23 | 2002 | 116.1
24 | 2003 | 117.9
25 | 2004 | 116.6
26 | 2005 | 112.5
27 | 2006 | 117.3
28 | 2007 | 110.9
29 | 2008 | 114.6
30

## A4
4) Calculate the exponential smoothing models using Excel damping factors 0.8 and 0.2 For each of the exponential smoothing models forecast the average number of rushing yards in the NFL for the 2009 season.
|  |  | smoother | more weight on most recent value
| Year (x) | Rushing yards/Game (y) | dampfact=0.8 | dampfact=0.2
1 | 1980 | 127.5 | #N/A | #N/A | Forecast for 2009 with 0.8 damping factor:
2 | 1981 | 130.1 | 127.5 | 127.5 | 113.9066
3 | 1982 | 117.8 | 128.02 | 129.58
4 | 1983 | 129.7 | 125.976 | 120.156
5 | 1984 | 123.9 | 126.7208 | 127.7912
6 | 1985 | 124.9 | 126.1566 | 124.6782
7 | 1986 | 118.7 | 125.9053 | 124.8556
8 | 1987 | 123.9 | 124.4642 | 119.9311
9 | 1988 | 121.4 | 124.3514 | 123.1062
10 | 1989 | 115.3 | 123.7611 | 121.7412
11 | 1990 | 113.9 | 122.0689 | 116.5882
12 | 1991 | 107.7 | 120.4351 | 114.4376
13 | 1992 | 110.5 | 117.8881 | 109.0475
14 | 1993 | 110 | 116.4105 | 110.2095
15 | 1994 | 104.3 | 115.1284 | 110.0419
16 | 1995 | 108.1 | 112.9627 | 105.4484
17 | 1996 | 109 | 111.9902 | 107.5697
18 | 1997 | 113 | 111.3921 | 108.7139
19 | 1998 | 112.7 | 111.7137 | 112.1428
20 | 1999 | 106.5 | 111.911 | 112.5886 | Forecast for 2009 with 0.2 damping factor:
21 | 2000 | 112.6 | 110.8288 | 107.7177 | 114.0844
22 | 2001 | 111.8 | 111.183 | 111.6235
23 | 2002 | 116.1 | 111.3064 | 111.7647
24 | 2003 | 117.9 | 112.2651 | 115.2329
25 | 2004 | 116.6 | 113.3921 | 117.3666
26 | 2005 | 112.5 | 114.0337 | 116.7533
27 | 2006 | 117.3 | 113.7269 | 113.3507
28 | 2007 | 110.9 | 114.4416 | 116.5101
29 | 2008 | 114.6 | 113.7332 | 112.022
30 | 2009 |  | 113.9066 | 114.0844

## A5
5) Calculate a moving average model using k=5 (Excel interval). Forecast the average number of rushing yards in the NFL for the 2009 season.
|  | output(y) | k=5
| Year (x) | Rushing yards/Game (y) | moving avg
1 | 1980 | 127.5
2 | 1981 | 130.1 | #N/A
3 | 1982 | 117.8 | #N/A
4 | 1983 | 129.7 | #N/A
5 | 1984 | 123.9 | #N/A
6 | 1985 | 124.9 | 125.8
7 | 1986 | 118.7 | 125.28
8 | 1987 | 123.9 | 123
9 | 1988 | 121.4 | 124.22
10 | 1989 | 115.3 | 122.56
11 | 1990 | 113.9 | 120.84
12 | 1991 | 107.7 | 118.64
13 | 1992 | 110.5 | 116.44
14 | 1993 | 110 | 113.76
15 | 1994 | 104.3 | 111.48
16 | 1995 | 108.1 | 109.28
17 | 1996 | 109 | 108.12
18 | 1997 | 113 | 108.38
19 | 1998 | 112.7 | 108.88
20 | 1999 | 106.5 | 109.42
21 | 2000 | 112.6 | 109.86
22 | 2001 | 111.8 | 110.76
23 | 2002 | 116.1 | 111.32 | 2009 NFL Season, Forecasted Avg Rushing Yards:
24 | 2003 | 117.9 | 111.94 | 114.38
25 | 2004 | 116.6 | 112.98
26 | 2005 | 112.5 | 115
27 | 2006 | 117.3 | 114.98
28 | 2007 | 110.9 | 116.08
29 | 2008 | 114.6 | 115.04
30 |  |  | 114.38